## Foglio1
CONNECTION NODES |  |  | Object | [8 empty] | PROGRESS
General | FROM | TO
REF | Substation | Substation | Element | System | Construction | Type | Length (km) | AC voltage (kV) | DC voltage (kV) | Nominal Capacity (MVA)** | Brief description of the project | Present status | Expected Date of commissioning
Interconnection Austria | Lienz | Veneto region | line | single circuit | OHL | new | 100 - 150 | 380 ÷ 400 |  | 1500 MVA | The project foresees a reconstruction of the existing 220-kV-interconnection line as 380-kV-line on an optimized route to minimize the environmental impact. | under consideration | long term
Interconnection Austria | Prati di Vizze (IT) | Steinach (AT) | line | single circuit | OHL | upgrade | 44 | 110 ÷ 132 |  | 100 MVA | The project comprises the upgrading of the existing line Prati di Vizze (IT) – Steinach (AT), currently operated at medium voltage and the installation of a 110-kV/132-kV PST in Steinach (AT) | planned | 2011
Sicily | Chiaramonte Gulfi | Sorgente | line | single circuit | OHL | new | 365 | 380 ÷ 400 |  | 1500 MVA | Realization of 380 kV ring grid, trough the construction of 3 new 380 kV line: "Chiaramonte Gulfi - Ciminna", "Sorgente - Ciminna" and "Paternò - Priolo". It will be realized a new 380/150 kV substation in Caltanissetta area and the voltage upgrade of the existing Ciminna substation up to 380 kV. | planned | 2015
Sicily | Sorgente | Rizziconi | line | double circuit | subsea cable | new | 90 | 380 ÷ 400 |  | 2 x 1500 MVA | The new double circuit 380 kV line consists of a part subsea cable and in the remainder a OHL. | under construction | 2013
Sicily | Partanna | Ciminna | line | single circuit | OHL | new | 65 | 380 ÷ 400 |  | 1500 MVA | It will be constructed a new 380 kV line between Partanna and Ciminna substations. | planned | long term
Sicily | Partinico | Fulgatore | line | single circuit | OHL | new | 45 | 380 ÷ 400 |  | 1500 MVA | A new 380 kV line between Partinico and Fulgatore in Western Sicily | planned | 2015
North West | Trino | Lacchiarella | line | double circuit | OHL | new | 95 | 380 ÷ 400 |  | 2 x 1500 MVA | A new 380 kV line between the existing 380 kV substations of Trino and Lacchiarella in North West Italy area. | design&permitting | 2012
North West | Chignolo Po | Maleo | line | double circuit | OHL | new | 22 | 380 ÷ 400 |  | 2 x 1500 MVA | A new 380 kV line between the new 380 kV substations of Chignolo Po and Maleo in Lodi area. Restructuring of HV network. | under consideration | 2012
North West | Casanova | Vignole | line | single circuit | OHL | upgrade | 100 | 380 ÷ 400 |  | 1500 MVA | Realization of a voltage upgrade of the existing 220 kV line from Casanova to Vignole substations up to 380 kV and a new 380/220/150 kV substation in Asti area. | planned | 2014/long term
North West | Voghera | La Casella | line | double circuit | OHL | new | 45 | 380 ÷ 400 |  | 2 x 1500 MVA | Realization of a new 380 kV line between the existing 380 kV substations of La casella and Voghera. | planned | long term
South | Foggia (PST) | Villanova (PST) | line/PST | double circuit | OHL | new | 170 | 380 ÷ 400 |  | 2 x 1500 MVA | Realization of a new 380 kV line between the existing 380 kV of Foggia and Villanova, connected in and out to the Larino and Gissi substations. PST on the future 380kV line. | planned | 2013/2014
South | Feroleto | Maida | line | single circuit | OHL | new | 7 | 380 ÷ 400 |  | 1500 MVA | Realization of a new 380 kV line across Calabria between the existing 380 kV of Feroleto and the future substation of Maida. Rearrangement North Calabria grid. | design&permitting | 2011
South | Montecorvino | Benevento | line | double circuit | OHL | new | 70 | 380 ÷ 400 |  | 2 x 1500 MVA | Realization of a new 380 kV line between the existing 380 kV of Montecorvino and Benevento II, providing the connection in and out to the future substation to be build in Avellino North area, which will be also connected the existing 380 kV line "Matera-S. Sofia". | design&permitting | 2011/2013
Center | Fano | Teramo | line | single circuit | OHL | new | 200 | 380 ÷ 400 |  | 1500 MVA | Realization of a new 380 kV line between the existing 380 kV of Fano and Teramo, providing the connection in and out to the future substation to be build in Macerata area. | planned | 2015
Center North | Calenzano | Colunga | line | single circuit | OHL | upgrade | 80 | 380 ÷ 400 |  | 1500 MVA | It will be realized a voltage upgrade of the existing 220 kV line from Calenzano to Colunga substations up to 380 kV, providing the connection in and out to the existing substation 220/150 kV of S. Benedetto del Querceto made of 380 kV class. | design&permitting | 2013
South | Foggia | Benevento II | line | single circuit | OHL | upgrade | 85 | 380 ÷ 400 |  | 1500 MVA | Reinforcement of the existing 380 kV line between Foggia and Benevento II substations. PST on the 380 kV line. | design&permitting | 2012
North Est | West Udine | Redipuglia | line | double circuit | OHL | new | 40 | 380 ÷ 400 |  | 2 x 1500 MVA | Realization of a new 380 kV line between the existing substation of West Udine and Redipuglia, providing the connection in and out to the future substation of South Udine. | design&permitting | 2012
North Est | Dolo | Camin | line | double circuit | OHL | new | 15 | 380 ÷ 400 |  | 2 x 1500 MVA | A new 380 kV line between Dolo and Camin substations, to be build in parallel with the existing one between the same nodes. | design&permitting | 2011/2013
North | Sermide | Carpi | line | single circuit | OHL | new | 35 | 380 ÷ 400 |  | 1500 MVA | Realization of a new 380 kV line between the existing substation of Sermide and Carpi. | planned | long term
South | Deliceto | Bisaccia | line | single circuit | OHL | new | 30 | 380 ÷ 400 |  | 1500 MVA | A new 380 kV line between the future substations of Deliceto and Bisaccia, in the Candela area. | planned | 2013
North West | Avise | Chatillon | line | single circuit | OHL | upgrade | 40 | 380 ÷ 400 |  | 1500 MVA | Voltage upgrade of the existing 220 kV lines "Avise-Villeneuve" and "Villeneuve-Chatillon" up to 380 kV, exercises to 220 kV. | planned | 2012
Interconnection Montenegro | Villanova | Tivat | line |  | subsea cable | new | 375 |  | 500 | 1000 MW | New HVDC interconnection line in the Easth part of the border, between Italy and Montenegro. Project includes new converter substations in both ending points. | planned | 2014/2015
Interconnection Croazia | Candia | Konjsko | line |  | subsea cable | new | 280 |  | 500 | 1000 MW | New HVDC interconnection line in the Easth part of the border, between Italy and Croatia. Project includes new converter substations in both ending points. | under consideration | long term
Sardinia | Ittiri | Codrongianos | line | single circuit | OHL | new | 18 | 380 ÷ 400 |  | 1500 MVA | Realization of a new 380 kV line between the existing substation of Codrongianos and the future 380 kV substation of Ittiri, connected in and out to the 380 kV line "Fiumesanto-Selargius". | under construction | 2010/2011
Sardinia -mainland | Fiumesanto | Latina | line |  | subsea cable | new | 420 |  | 400 kV | 1000 MW | Second pole HVDC line between Sardinia and mainland Italy. (first pole in operation in 2009) | under construction | 2010
Center North | Casellina | Tavarnuzze | line | single circuit | OHL | new | 37 | 380 ÷ 400 |  | 1500 MVA | Rearrangement of EHV grid in the area between Casellina and S. Barbara. Voltage upgrade of the existing substations of Casellina and S. Barbara. | under construction | 2010
Interconnection insulated system | Porto Ferraio (Elba Island) | Cornia (Piombino) | line | single circuit | subsea cable | new | 40 | 220 ÷<220 |  | 200 MVA | Realization of a new 132 kV line between the existing substation of Porto Ferraio and the future 380/132 kV substation of Cornia, connected in and out to the 380 kV line "Suvereto-Piombino Termica". | planned | 2012
Interconnection insulated system | Capri, Ischia, Procida |  | line | single circuit | subsea cable | new | 95 | 220 ÷<220 |  | 200 MVA | Realization of a new 150 kV line between the Capri, Ischia and Procida islands to the existing substations of Cuma and Torre Annunziata (mainland Italy). | planned | 2014
Interconnection Tunisia | El Aouaria | Partanna | line | single circuit | subsea cable | new | 350 |  | 400kV | 500 MW | HVDC line between Tunisia and mainland Italy | design&permitting | long term
** the nominal capacity is a value used to designate and identify a component