## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 21/03/2017 until 31/12/2017 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 21-03-2017
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201601336 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-04-03 07:30 | 2017-04-07 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/01/2017 16:00
CA-201601340 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-07-03 08:00 | 2017-07-21 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601340 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-07-03 08:00 | 2017-07-21 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601340 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-07-03 08:00 | 2017-07-21 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601340 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-07-03 08:00 | 2017-07-21 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 06/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CA-201601783 | --- | Substation | IntraZonal | Upgrading | 2017-04-20 08:00 | 2017-04-21 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 10/03/2017 16:00
CA-201601811 | --- | Substation | IntraZonal | Maintenance | 2017-03-23 08:00 | 2017-03-24 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201601862 | --- | Substation | IntraZonal | Maintenance | 2017-05-08 08:00 | 2017-05-11 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 02/12/2016 17:00
CA-201601862 | --- | Substation | IntraZonal | Maintenance | 2017-05-08 08:00 | 2017-05-11 16:00 | CSUD | SARD | Look Up | 690 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 02/12/2016 17:00
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-10-02 07:30 | 2017-10-05 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-10-02 07:30 | 2017-10-05 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201601923 | --- | Substation | IntraZonal | Upgrading | 2017-04-18 08:00 | 2017-04-18 17:00 | SARD | COAC | Look Up | 45 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 10/03/2017 16:00
CA-201601925 | --- | Substation | IntraZonal | Upgrading | 2017-04-19 08:00 | 2017-04-19 17:00 | SARD | COAC | Look Up | 45 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201700050 | --- | AC Link | IntraZonal | Maintenance | 2017-03-29 08:00 | 2017-03-30 16:30 | SARD | COAC | Look Up | 40 | Valid on Working days from 08:00 till 16:30 | Working days |  |  | 08:00 - 16:30 | Planned | v.1 - 18/01/2017 16:00
CA-201700051 | --- | AC Link | IntraZonal | Maintenance | 2017-04-01 08:00 | 2017-04-02 16:30 | SARD | COAC | Look Up | 40 | Valid on Working days from 08:00 till 16:30 | Working days |  |  | 08:00 - 16:30 | Planned | v.1 - 18/01/2017 16:00
CA-201700051 | --- | AC Link | IntraZonal | Maintenance | 2017-04-01 08:00 | 2017-04-02 16:30 | SARD | COAC | Look Up | 40 | Valid on Holidays from 08:00 till 16:30 | Holidays |  |  | 08:00 - 16:30 | Planned | v.1 - 18/01/2017 16:00
CC-201601833 | --- --- --- --- --- --- --- | AC Link Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2017-03-20 08:00 | 2017-03-31 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 10/03/2017 16:00 v.1 - 02/03/2017 17:00
CC-201601833 | --- --- --- --- --- --- --- | AC Link Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2017-03-20 08:00 | 2017-03-31 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 10/03/2017 16:00 v.1 - 02/03/2017 17:00
CC-201601837 | --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-04-03 08:00 | 2017-04-07 16:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601841 | --- | AC Link | IntraZonal | Maintenance | 2017-04-01 08:00 | 2017-04-02 16:00 | SUD | CSUD | Look Up | 3500 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601842 | --- | AC Link | IntraZonal | Maintenance | 2017-04-08 08:00 | 2017-04-09 16:00 | SUD | CSUD | Look Up | 3500 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601847 | --- | AC Link | IntraZonal | Maintenance | 2017-04-10 08:00 | 2017-04-14 16:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601848 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601848 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601848 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601849 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601849 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601849 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-17 08:00 | 2017-04-21 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601852 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601852 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601852 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601852 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601853 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-04-23 08:00 | 2017-04-28 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601882 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-06-20 08:00 | 2017-06-30 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601882 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-06-20 08:00 | 2017-06-30 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601883 | --- | AC Link | IntraZonal | Upgrading | 2017-09-12 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601883 | --- | AC Link | IntraZonal | Upgrading | 2017-09-12 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601884 | --- | AC Link | IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-12 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601884 | --- | AC Link | IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-12 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601886 | --- | AC Link | IntraZonal | Upgrading | 2017-05-02 08:00 | 2017-05-04 18:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 08:00 till 18:00 | Working days |  |  | 08:00 - 18:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601928 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-02 08:00 | 2017-05-14 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601928 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-02 08:00 | 2017-05-14 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601928 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-02 08:00 | 2017-05-14 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601928 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-02 08:00 | 2017-05-14 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601929 | --- --- --- --- --- | Substation AC Link AC Link AC Link Substation | IntraZonal CrossZonal CrossZonal CrossZonal IntraZonal | Upgrading | 2017-06-24 08:00 | 2017-07-02 16:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 27/01/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601929 | --- --- --- --- --- | Substation AC Link AC Link AC Link Substation | IntraZonal CrossZonal CrossZonal CrossZonal IntraZonal | Upgrading | 2017-06-24 08:00 | 2017-07-02 16:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 27/01/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601929 | --- --- --- --- --- | Substation AC Link AC Link AC Link Substation | IntraZonal CrossZonal CrossZonal CrossZonal IntraZonal | Upgrading | 2017-06-24 08:00 | 2017-07-02 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 27/01/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601929 | --- --- --- --- --- | Substation AC Link AC Link AC Link Substation | IntraZonal CrossZonal CrossZonal CrossZonal IntraZonal | Upgrading | 2017-06-24 08:00 | 2017-07-02 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 27/01/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601930 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-06-05 08:00 | 2017-06-19 17:00 | ROSN | SUD | Look Up | 550 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601930 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-06-05 08:00 | 2017-06-19 17:00 | ROSN | SUD | Look Up | 550 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601930 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-06-05 08:00 | 2017-06-19 17:00 | SUD | CSUD | Look Up | 2800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601930 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-06-05 08:00 | 2017-06-19 17:00 | SUD | CSUD | Look Up | 2800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601931 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-07 08:00 | 2017-05-07 16:00 | ROSN | SUD | Look Up | 550 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601931 | --- --- --- | AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal | Upgrading | 2017-05-07 08:00 | 2017-05-07 16:00 | SUD | CSUD | Look Up | 2800 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601932 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-05-14 08:00 | 2017-05-15 16:00 | ROSN | SUD | Look Up | 1000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601932 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-05-14 08:00 | 2017-05-15 16:00 | ROSN | SUD | Look Up | 1000 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601932 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-05-14 08:00 | 2017-05-15 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601932 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-05-14 08:00 | 2017-05-15 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601933 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-05-16 08:00 | 2017-05-20 16:00 | ROSN | SUD | Look Up | 1000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601933 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-05-16 08:00 | 2017-05-20 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601934 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2017-05-15 08:00 | 2017-05-21 18:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601934 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2017-05-15 08:00 | 2017-05-21 18:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601935 | --- --- --- --- --- --- | Substation Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2017-05-21 08:00 | 2017-06-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601935 | --- --- --- --- --- --- | Substation Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2017-05-21 08:00 | 2017-06-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601936 | --- --- --- | AC Link Substation Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2017-06-26 08:00 | 2017-06-29 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601937 | --- | Substation | IntraZonal | Maintenance | 2017-06-30 08:00 | 2017-06-30 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601939 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2017-08-07 08:00 | 2017-08-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 01/02/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601944 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-08-21 08:00 | 2017-08-25 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601946 | --- | AC Link | IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-05 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601950 | --- --- --- --- | AC Link Substation AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2017-09-18 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601951 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2017-09-12 08:00 | 2017-09-13 15:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal | Maintenance | 2017-09-26 07:00 | 2017-10-06 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal | Maintenance | 2017-09-26 07:00 | 2017-10-06 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal | Maintenance | 2017-09-26 07:00 | 2017-10-06 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal | Maintenance | 2017-09-26 07:00 | 2017-10-06 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601970 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601970 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3500 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601971 | --- | AC Link | IntraZonal | Upgrading | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 12/01/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601971 | --- | AC Link | IntraZonal | Upgrading | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 12/01/2017 18:00 v.1 - 02/12/2016 17:00
CC-201700006 | --- | AC Link | IntraZonal | Maintenance | 2017-04-03 08:00 | 2017-04-07 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 04/01/2017 17:00
CC-201700098 | --- | AC Link | CrossZonal | Maintenance | 2017-04-07 08:00 | 2017-04-09 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 24/01/2017 17:00
CC-201700098 | --- | AC Link | CrossZonal | Maintenance | 2017-04-07 08:00 | 2017-04-09 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 24/01/2017 17:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700297 | --- | Substation | IntraZonal | Maintenance | 2017-03-21 08:00 | 2017-03-24 18:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 03/03/2017 17:00
PA-201601967 | --- | AC Link | IntraZonal | Maintenance | 2017-04-10 08:00 | 2017-04-12 15:00 | ROSN | SICI | Look Up | 850 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
PA-201601967 | --- | AC Link | IntraZonal | Maintenance | 2017-04-10 08:00 | 2017-04-12 15:00 | SICI | ROSN | Look Up | 850 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
PA-201700291 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2017-03-21 08:00 | 2017-03-22 16:00 | ROSN | SICI | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/03/2017 17:00
PA-201700291 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2017-03-21 08:00 | 2017-03-22 16:00 | SICI | ROSN | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/03/2017 17:00
PA-201700293 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2017-03-23 08:00 | 2017-03-24 16:00 | ROSN | SICI | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/03/2017 17:00
PA-201700293 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2017-03-23 08:00 | 2017-03-24 16:00 | SICI | ROSN | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/03/2017 17:00