## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 19/07/2017 until 31/12/2017 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 19-07-2017
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201601339 | --- --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-10-13 17:00 | 2017-10-29 17:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201601339 | --- --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-10-13 17:00 | 2017-10-29 17:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201601339 | --- --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-10-13 17:00 | 2017-10-29 17:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201601339 | --- --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-10-13 17:00 | 2017-10-29 17:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601350 | --- | AC Link | IntraZonal | Upgrading | 2017-10-16 08:00 | 2017-10-20 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601351 | --- | AC Link | IntraZonal | Upgrading | 2017-10-23 08:00 | 2017-10-27 17:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 06/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 02/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 02/12/2016 17:00
CA-201601352 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-10 16:00 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Cancelled | v.2 - 06/07/2017 17:00 v.1 - 02/12/2016 17:00
CA-201601862 | --- | Substation | IntraZonal | Maintenance | 2017-10-23 08:00 | 2017-10-26 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 27/04/2017 16:00
CA-201601862 | --- | Substation | IntraZonal | Maintenance | 2017-10-23 08:00 | 2017-10-26 16:00 | CSUD | SARD | Look Up | 690 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 27/04/2017 16:00
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-10-02 07:30 | 2017-10-05 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-10-02 07:30 | 2017-10-05 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CA-201601919 | --- | AC Link | IntraZonal | Upgrading | 2017-11-13 08:00 | 2017-12-01 17:00 | SARD | COAC | Look Up | 80 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 23/05/2017 16:00
CA-201700362 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-18 07:59 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700362 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-18 07:59 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700362 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-18 07:59 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700362 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-18 07:59 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CNOR | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CORS | CNOR | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CA-201700363 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-18 08:00 | 2017-10-13 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 29/03/2017 18:00
CC-201601858 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601858 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601859 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-11-05 08:00 | 2017-11-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601874 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601875 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2017-11-12 08:00 | 2017-11-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601877 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601879 | --- | AC Link | CrossZonal | Upgrading | 2017-10-02 07:00 | 2017-10-31 18:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601883 | --- | AC Link | IntraZonal | Upgrading | 2017-09-12 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 03/07/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601883 | --- | AC Link | IntraZonal | Upgrading | 2017-09-12 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 03/07/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601884 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-12 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601884 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-11-06 08:00 | 2017-11-12 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601886 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-06 18:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 08:00 till 18:00 | Working days |  |  | 08:00 - 18:00 | Planned | v.1 - 20/04/2017 17:00
CC-201601939 | --- --- --- --- | AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-08-07 08:00 | 2017-08-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 01/02/2017 17:00 v.1 - 02/12/2016 17:00
CC-201601944 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-08-21 08:00 | 2017-08-25 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601946 | --- | AC Link | IntraZonal | Maintenance | 2017-09-04 08:00 | 2017-09-05 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601950 | --- --- --- --- | AC Link Substation AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2017-09-18 08:00 | 2017-09-22 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601951 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2017-09-12 08:00 | 2017-09-13 15:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601959 | --- --- --- | AC Link Substation AC Link | CrossZonal IntraZonal IntraZonal | Maintenance | 2017-10-09 08:00 | 2017-10-13 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link AC Link AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-09-26 07:00 | 2017-10-06 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link AC Link AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-09-26 07:00 | 2017-10-06 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link AC Link AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-09-26 07:00 | 2017-10-06 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601969 | --- --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link AC Link AC Link | CrossZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2017-09-26 07:00 | 2017-10-06 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601970 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3500 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601970 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3500 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 02/12/2016 17:00
CC-201601971 | --- | AC Link | IntraZonal | Upgrading | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 12/01/2017 18:00 v.1 - 02/12/2016 17:00
CC-201601971 | --- | AC Link | IntraZonal | Upgrading | 2017-10-14 08:00 | 2017-10-27 17:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 12/01/2017 18:00 v.1 - 02/12/2016 17:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700101 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-09-23 08:00 | 2017-09-24 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 17/02/2017 18:00 v.1 - 25/01/2017 16:00
CC-201700416 | --- | Substation | IntraZonal | Maintenance | 2017-09-07 09:00 | 2017-09-08 15:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 09:00 till 15:00 | Working days |  |  | 09:00 - 15:00 | Planned | v.1 - 27/03/2017 18:00
CC-201700501 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-08-01 06:00 | 2017-08-04 18:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 06:00 till 18:00 | Working days |  |  | 06:00 - 18:00 | Updated | v.2 - 07/07/2017 16:00 v.1 - 06/06/2017 16:00
CC-201700501 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-08-01 06:00 | 2017-08-04 18:00 | NORD | CNOR | Look Up | 2200 | Valid on Working days from 06:00 till 18:00 | Working days |  |  | 06:00 - 18:00 | Updated | v.2 - 07/07/2017 16:00 v.1 - 06/06/2017 16:00
CC-201700551 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-08-29 08:00 | 2017-08-30 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 26/04/2017 16:00
CC-201700551 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2017-08-29 08:00 | 2017-08-30 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 26/04/2017 16:00
CC-201700552 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | CNOR | NORD | Look Up | 1000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | CNOR | NORD | Look Up | 1000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | NORD | CNOR | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | NORD | CNOR | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700553 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2017-08-01 08:00 | 2017-08-05 18:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 26/04/2017 16:00
IG-201700010 | --- | AC Link | CrossZonal | Forced outage | 2017-07-18 17:29 | 2017-07-19 11:34 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.1 - 18/07/2017 17:45 v.2 - 18/07/2017 22:30 v.3 - 19/07/2017 11:45
IG-201700010 | --- | AC Link | CrossZonal | Forced outage | 2017-07-18 17:29 | 2017-07-19 11:34 | CSUD | CNOR | Look Up | 1000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.1 - 18/07/2017 17:45 v.2 - 18/07/2017 22:30 v.3 - 19/07/2017 11:45
IG-201700011 | --- | AC Link | IntraZonal | Forced outage | 2017-07-19 12:43 | 2017-07-19 16:56 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.1 - 19/07/2017 13:15 v.2 - 19/07/2017 17:15