## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 21/11/2017 until 31/12/2017 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 21-11-2017
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-12-04 07:30 | 2017-12-07 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 14/09/2017 17:00
CA-201601869 | --- | AC Link | IntraZonal | Maintenance | 2017-12-04 07:30 | 2017-12-07 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 07:00 till 17:00 | Working days |  |  | 07:00 - 17:00 | Planned | v.1 - 14/09/2017 17:00
CA-201701669 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Forced outage | 2017-12-04 08:00 | 2017-12-10 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 21/11/2017 18:00
CA-201701669 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Forced outage | 2017-12-04 08:00 | 2017-12-10 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 21/11/2017 18:00
CA-201701669 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Forced outage | 2017-12-04 08:00 | 2017-12-10 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 21/11/2017 18:00
CA-201701669 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Forced outage | 2017-12-04 08:00 | 2017-12-10 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 21/11/2017 18:00
CC-201700552 | --- --- --- --- | AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | CNOR | NORD | Look Up | 1000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- --- --- | AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | CNOR | NORD | Look Up | 1000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- --- --- | AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | NORD | CNOR | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201700552 | --- --- --- --- | AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2017-11-25 08:00 | 2017-12-01 16:00 | NORD | CNOR | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 20/06/2017 18:00 v.1 - 26/04/2017 16:00
CC-201701439 | --- | DC Link | CrossZonal | Forced outage | 2017-10-10 | 2017-12-20 23:59 | BRNN | GREC | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 18/10/2017 18:00 v.4 - 16/10/2017 16:00 v.3 - 11/10/2017 17:00 v.2 - 10/10/2017 18:00 v.1 - 09/10/2017 17:00
CC-201701439 | --- | DC Link | CrossZonal | Forced outage | 2017-10-10 | 2017-12-20 23:59 | BRNN | GREC | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 18/10/2017 18:00 v.4 - 16/10/2017 16:00 v.3 - 11/10/2017 17:00 v.2 - 10/10/2017 18:00 v.1 - 09/10/2017 17:00
CC-201701439 | --- | DC Link | CrossZonal | Forced outage | 2017-10-10 | 2017-12-20 23:59 | GREC | BRNN | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 18/10/2017 18:00 v.4 - 16/10/2017 16:00 v.3 - 11/10/2017 17:00 v.2 - 10/10/2017 18:00 v.1 - 09/10/2017 17:00
CC-201701439 | --- | DC Link | CrossZonal | Forced outage | 2017-10-10 | 2017-12-20 23:59 | GREC | BRNN | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 18/10/2017 18:00 v.4 - 16/10/2017 16:00 v.3 - 11/10/2017 17:00 v.2 - 10/10/2017 18:00 v.1 - 09/10/2017 17:00
CC-201701440 | --- | AC Link | IntraZonal | Maintenance | 2017-11-20 08:00 | 2017-11-24 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.4 - 16/10/2017 16:00 v.3 - 11/10/2017 17:00 v.2 - 10/10/2017 18:00 v.1 - 09/10/2017 17:00
CC-201701455 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2017-11-26 07:00 | 2017-11-26 17:00 | SUD | CSUD | Look Up | 2800 | Valid on Holidays from 07:00 till 17:00 | Holidays |  |  | 07:00 - 17:00 | Updated | v.2 - 16/10/2017 16:00 v.1 - 11/10/2017 17:00
CC-201701498 | --- | AC Link | CrossZonal | Maintenance | 2017-11-21 08:00 | 2017-11-22 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 23/10/2017 17:00
CC-201701498 | --- | AC Link | CrossZonal | Maintenance | 2017-11-21 08:00 | 2017-11-22 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 23/10/2017 17:00
CC-201701499 | --- | AC Link | CrossZonal | Maintenance | 2017-11-23 08:00 | 2017-11-24 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 23/10/2017 17:00
CC-201701499 | --- | AC Link | CrossZonal | Maintenance | 2017-11-23 08:00 | 2017-11-24 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 23/10/2017 17:00
CC-201701530 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2017-11-26 08:00 | 2017-11-26 15:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 08:00 till 15:00 | Holidays |  |  | 08:00 - 15:00 | Updated | v.2 - 14/11/2017 18:00 v.1 - 06/11/2017 17:00
CC-201701531 | --- | Substation | IntraZonal | Maintenance | 2017-11-27 08:00 | 2017-11-27 12:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 12:00 | Working days |  |  | 08:00 - 12:00 | Planned | v.1 - 06/11/2017 17:00
CC-201701532 | --- | Substation | IntraZonal | Maintenance | 2017-11-27 12:00 | 2017-11-27 17:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 12:00 till 17:00 | Working days |  |  | 12:00 - 17:00 | Planned | v.1 - 06/11/2017 17:00
CC-201701538 | --- | AC Link | IntraZonal | Maintenance | 2017-11-27 10:00 | 2017-11-27 13:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 10:00 till 13:00 | Working days |  |  | 10:00 - 13:00 | Cancelled | v.2 - 14/11/2017 18:00 v.1 - 06/11/2017 17:00
CC-201701539 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2017-11-27 08:00 | 2017-12-01 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/11/2017 18:00 v.1 - 06/11/2017 17:00
CC-201701615 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-11-20 07:00 | 2017-11-21 17:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/11/2017 18:00
CC-201701650 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-12-04 09:00 | 2017-12-07 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 16/11/2017 18:00
CC-201701652 | --- | Substation | IntraZonal | Maintenance | 2017-12-08 09:00 | 2017-12-10 15:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 09:00 till 15:00 | Working days |  |  | 09:00 - 15:00 | Planned | v.1 - 16/11/2017 18:00
CC-201701652 | --- | Substation | IntraZonal | Maintenance | 2017-12-08 09:00 | 2017-12-10 15:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 09:00 till 15:00 | Holidays |  |  | 09:00 - 15:00 | Planned | v.1 - 16/11/2017 18:00
CC-201701653 | --- | Substation | IntraZonal | Maintenance | 2017-12-27 09:00 | 2017-12-28 15:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 09:00 till 15:00 | Working days |  |  | 09:00 - 15:00 | Planned | v.1 - 16/11/2017 18:00
CC-201701656 | --- | AC Link | IntraZonal | Upgrading | 2017-12-02 08:00 | 2017-12-03 15:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 16/11/2017 18:00
CC-201701656 | --- | AC Link | IntraZonal | Upgrading | 2017-12-02 08:00 | 2017-12-03 15:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 16/11/2017 18:00
CC-201701674 | --- | AC Link | IntraZonal | Upgrading | 2017-12-16 09:00 | 2017-12-17 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 17/11/2017 18:00
CC-201701674 | --- | AC Link | IntraZonal | Upgrading | 2017-12-16 09:00 | 2017-12-17 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 17/11/2017 18:00
CC-201701746 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2017-12-12 08:00 | 2017-12-12 15:00 | ROSN | SUD | Look Up | 2250 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 21/11/2017 18:00
PA-201701648 | --- | Substation | IntraZonal | Forced outage | 2017-11-21 08:00 | 2017-11-21 12:00 | ROSN | SICI | Look Up | 900 | Valid on Working days from 08:00 till 12:00 | Working days |  |  | 08:00 - 12:00 | Planned | v.1 - 16/11/2017 18:00
PA-201701648 | --- | Substation | IntraZonal | Forced outage | 2017-11-21 08:00 | 2017-11-21 12:00 | SICI | ROSN | Look Up | 900 | Valid on Working days from 08:00 till 12:00 | Working days |  |  | 08:00 - 12:00 | Planned | v.1 - 16/11/2017 18:00