## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 14/02/2018 until 31/12/2018 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 14-02-2018
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201701210 | --- | AC Link | IntraZonal | Upgrading | 2018-02-12 07:30 | 2018-02-16 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 04/01/2018 15:00 v.1 - 07/12/2017 17:00
CA-201701213 | --- | AC Link | IntraZonal | Upgrading | 2018-02-19 07:30 | 2018-02-23 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 04/01/2018 15:00 v.1 - 07/12/2017 17:00
CA-201701229 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-16 07:30 | 2018-04-20 16:30 | CSUD | SARD | Look Up | 210 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 07/12/2017 17:00
CA-201701229 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-16 07:30 | 2018-04-20 16:30 | SARD | CSUD | Look Up | 720 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 07/12/2017 17:00
CA-201701238 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-23 08:00 | 2018-04-26 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CA-201701238 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-23 08:00 | 2018-04-26 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701250 | --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-28 08:00 | 2018-06-01 16:00 | CSUD | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701250 | --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-28 08:00 | 2018-06-01 16:00 | SARD | CSUD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 09/01/2018 17:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 09/01/2018 17:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 09/01/2018 17:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 09/01/2018 17:00
CA-201701261 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-12 16:00 | 2018-11-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 14/02/2018 17:00 v.1 - 07/12/2017 17:00
CA-201701261 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-12 16:00 | 2018-11-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 14/02/2018 17:00 v.1 - 07/12/2017 17:00
CA-201701261 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-12 16:00 | 2018-11-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 14/02/2018 17:00 v.1 - 07/12/2017 17:00
CA-201701261 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-12 16:00 | 2018-11-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 14/02/2018 17:00 v.1 - 07/12/2017 17:00
CA-201701262 | --- | AC Link | IntraZonal | Upgrading | 2018-11-28 07:30 | 2018-11-28 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 45 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701540 | --- | AC Link | IntraZonal | Upgrading | 2018-03-26 07:30 | 2018-04-06 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CA-201800052 | --- | Substation | IntraZonal | Upgrading | 2018-06-05 08:00 | 2018-06-05 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800053 | --- | Substation | IntraZonal | Upgrading | 2018-06-06 08:00 | 2018-06-07 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800058 | --- | Substation | IntraZonal | Upgrading | 2018-06-08 08:00 | 2018-06-08 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800059 | --- | Substation | IntraZonal | Upgrading | 2018-06-11 08:00 | 2018-06-11 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800062 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-12 08:00 | 2018-06-12 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800063 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-13 08:00 | 2018-06-13 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800066 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-14 08:00 | 2018-06-14 16:00 | SARD | COAC | Look Up | 60 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/01/2018 17:00
CA-201800070 | --- | Substation | IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-04 16:00 | SARD | COAC | Look Up | 60 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 12/01/2018 16:00
CA-201800193 | --- | Substation | IntraZonal | Maintenance | 2018-03-12 08:00 | 2018-03-13 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 06/02/2018 17:00
CA-201800193 | --- | Substation | IntraZonal | Maintenance | 2018-03-12 08:00 | 2018-03-13 16:00 | CSUD | SARD | Look Up | 690 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 06/02/2018 17:00
CC-201701765 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-06 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701783 | --- --- --- --- --- | Substation AC Link Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-19 08:00 | 2018-02-25 16:00 | ROSN | SUD | Look Up | 2000 | Valid on Working days from 00:00 till 05:59 | Working days |  |  | 00:00 - 05:59 | Planned | v.1 - 19/01/2018 17:00
CC-201701783 | --- --- --- --- --- | Substation AC Link Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-19 08:00 | 2018-02-25 16:00 | ROSN | SUD | Look Up | 2250 | Valid on Working days from 06:00 till 21:59 | Working days |  |  | 06:00 - 21:59 | Planned | v.1 - 19/01/2018 17:00
CC-201701783 | --- --- --- --- --- | Substation AC Link Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-19 08:00 | 2018-02-25 16:00 | ROSN | SUD | Look Up | 2000 | Valid on Working days from 22:00 till 23:59 | Working days |  |  | 22:00 - 23:59 | Planned | v.1 - 19/01/2018 17:00
CC-201701783 | --- --- --- --- --- | Substation AC Link Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-19 08:00 | 2018-02-25 16:00 | ROSN | SUD | Look Up | 2000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 19/01/2018 17:00
CC-201701785 | --- --- --- | Substation Substation Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-02-27 08:00 | 2018-03-02 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701786 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-03-05 08:00 | 2018-03-09 17:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701788 | --- | AC Link | CrossZonal | Upgrading | 2018-03-12 08:00 | 2018-03-12 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701789 | --- | AC Link | CrossZonal | Upgrading | 2018-03-13 08:00 | 2018-03-16 15:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701791 | --- --- --- --- | AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-03-17 08:00 | 2018-03-31 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701791 | --- --- --- --- | AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-03-17 08:00 | 2018-03-31 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701791 | --- --- --- --- | AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-03-17 08:00 | 2018-03-31 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701791 | --- --- --- --- | AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-03-17 08:00 | 2018-03-31 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701792 | --- | Substation | IntraZonal | Maintenance | 2018-03-19 08:00 | 2018-03-23 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701793 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-03-26 08:00 | 2018-03-30 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701796 | --- --- | AC Link Substation | CrossZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-09 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701796 | --- --- | AC Link Substation | CrossZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-09 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701797 | --- --- --- --- --- --- | Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-08 17:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701797 | --- --- --- --- --- --- | Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-08 17:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701810 | --- | AC Link | IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-22 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701810 | --- | AC Link | IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-22 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701812 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-12 08:00 | 2018-02-18 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 02/02/2018 18:00 v.1 - 25/01/2018 18:00
CC-201701812 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-12 08:00 | 2018-02-18 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 02/02/2018 18:00 v.1 - 25/01/2018 18:00
CC-201701812 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-12 08:00 | 2018-02-18 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 02/02/2018 18:00 v.1 - 25/01/2018 18:00
CC-201701812 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-02-12 08:00 | 2018-02-18 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 02/02/2018 18:00 v.1 - 25/01/2018 18:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-16 08:00 | 2018-04-30 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-16 08:00 | 2018-04-30 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-16 08:00 | 2018-04-30 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-16 08:00 | 2018-04-30 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701816 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-05 08:00 | 2018-05-25 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701816 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-05 08:00 | 2018-05-25 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701826 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 08:00 | 2018-05-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701826 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 08:00 | 2018-05-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701827 | --- --- --- | Substation Substation Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-25 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701828 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701829 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701829 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701829 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701829 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701837 | --- | AC Link | IntraZonal | Maintenance | 2018-05-28 08:00 | 2018-06-01 17:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 17:00 | Working days |  |  | 00:00 - 17:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-13 16:00 | ROSN | SUD | Look Up | 550 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-13 16:00 | ROSN | SUD | Look Up | 550 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-13 16:00 | SUD | CSUD | Look Up | 2800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-13 16:00 | SUD | CSUD | Look Up | 2800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701839 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-04 08:00 | 2018-06-08 16:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701840 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-07-08 08:00 | 2018-07-08 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701842 | --- --- --- --- | Substation Substation Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-08-06 08:00 | 2018-08-10 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701846 | --- --- --- | AC Link Substation Substation | CrossZonal IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 23/01/2018 18:00 v.1 - 07/12/2017 17:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701858 | --- | Substation | IntraZonal | Upgrading | 2018-08-26 08:00 | 2018-08-26 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701859 | --- | AC Link | IntraZonal | Upgrading | 2018-08-27 08:00 | 2018-08-27 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701860 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-28 08:00 | 2018-09-02 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701860 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-28 08:00 | 2018-09-02 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/12/2017 17:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/12/2017 17:00
CC-201701864 | --- | AC Link | CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701864 | --- | AC Link | CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701870 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-12 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701871 | --- | AC Link | IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/12/2017 17:00
CC-201701872 | --- --- --- --- --- --- | Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701872 | --- --- --- --- --- --- | Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701872 | --- --- --- --- --- --- | Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701872 | --- --- --- --- --- --- | Substation AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/12/2017 17:00
CC-201701976 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-07 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 29/01/2018 17:00 v.1 - 11/12/2017 17:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 31/01/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 700 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 31/01/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 31/01/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 700 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 31/01/2018 18:00
CC-201800197 | --- --- | AC Link Substation | IntraZonal IntraZonal | Forced outage | 2018-02-23 08:00 | 2018-02-23 16:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 06/02/2018 17:00
CC-201800198 | --- | Substation | IntraZonal | Maintenance | 2018-03-02 09:00 | 2018-03-02 18:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 09:00 till 18:00 | Working days |  |  | 09:00 - 18:00 | Updated | v.2 - 08/02/2018 17:00 v.1 - 06/02/2018 17:00
CC-201800234 | --- | Substation | IntraZonal | Maintenance | 2018-03-11 08:00 | 2018-03-11 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 14/02/2018 17:00 v.1 - 13/02/2018 17:00
CC-201800234 | --- | Substation | IntraZonal | Maintenance | 2018-03-11 08:00 | 2018-03-11 16:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 14/02/2018 17:00 v.1 - 13/02/2018 17:00
CC-201800234 | --- | Substation | IntraZonal | Maintenance | 2018-03-11 08:00 | 2018-03-11 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 14/02/2018 17:00 v.1 - 13/02/2018 17:00
CC-201800234 | --- | Substation | IntraZonal | Maintenance | 2018-03-11 08:00 | 2018-03-11 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 14/02/2018 17:00 v.1 - 13/02/2018 17:00
PA-201701893 | --- --- | Transformer Transformer | IntraZonal IntraZonal | Maintenance | 2018-04-09 08:00 | 2018-04-13 15:30 | ROSN | SICI | Look Up | 900 | Valid on Working days from 08:00 till 15:30 | Working days |  |  | 08:00 - 15:30 | Planned | v.1 - 19/01/2018 17:00
PA-201701893 | --- --- | Transformer Transformer | IntraZonal IntraZonal | Maintenance | 2018-04-09 08:00 | 2018-04-13 15:30 | SICI | ROSN | Look Up | 900 | Valid on Working days from 08:00 till 15:30 | Working days |  |  | 08:00 - 15:30 | Planned | v.1 - 19/01/2018 17:00
PA-201800120 | --- | Transformer | IntraZonal | Forced outage | 2018-02-07 08:00 | 2018-02-18 16:00 | ROSN | SICI | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/02/2018 17:00
PA-201800120 | --- | Transformer | IntraZonal | Forced outage | 2018-02-07 08:00 | 2018-02-18 16:00 | ROSN | SICI | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 14/02/2018 17:00
PA-201800120 | --- | Transformer | IntraZonal | Forced outage | 2018-02-07 08:00 | 2018-02-18 16:00 | SICI | ROSN | Look Up | 750 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/02/2018 17:00
PA-201800120 | --- | Transformer | IntraZonal | Forced outage | 2018-02-07 08:00 | 2018-02-18 16:00 | SICI | ROSN | Look Up | 750 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 14/02/2018 17:00