## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 11/04/2018 until 31/12/2018 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 11-04-2018
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201701229 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-16 08:00 | 2018-04-19 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 09/04/2018 17:00
CA-201701229 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-16 08:00 | 2018-04-19 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 09/04/2018 17:00
CA-201701238 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-23 08:00 | 2018-04-26 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201701238 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-04-23 08:00 | 2018-04-26 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701241 | --- | AC Link | IntraZonal | Upgrading | 2018-05-07 07:30 | 2018-05-12 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701242 | --- | AC Link | IntraZonal | Upgrading | 2018-05-14 07:30 | 2018-05-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 85 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701243 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 07:30 | 2018-05-28 16:30 | SARD | COAC | Look Up | 90 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701250 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-28 08:00 | 2018-06-01 16:00 | CSUD | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701250 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-28 08:00 | 2018-06-01 16:00 | SARD | CSUD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CNOR | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | CNOR | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701262 | --- | AC Link | IntraZonal | Upgrading | 2018-11-28 07:30 | 2018-11-28 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201800052 | --- | Substation | IntraZonal | Upgrading | 2018-06-05 08:00 | 2018-06-05 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800053 | --- | Substation | IntraZonal | Upgrading | 2018-06-06 08:00 | 2018-06-07 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800058 | --- | Substation | IntraZonal | Upgrading | 2018-06-08 08:00 | 2018-06-08 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800059 | --- | Substation | IntraZonal | Upgrading | 2018-06-11 08:00 | 2018-06-11 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800062 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-12 08:00 | 2018-06-12 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800063 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-13 08:00 | 2018-06-13 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800066 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-06-14 08:00 | 2018-06-14 16:00 | SARD | COAC | Look Up | 60 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800070 | --- | Substation | IntraZonal | Upgrading | 2018-06-04 08:00 | 2018-06-04 16:00 | SARD | COAC | Look Up | 60 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800256 | --- | AC Link | IntraZonal | Maintenance | 2018-06-21 08:00 | 2018-06-21 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800257 | --- | Substation | IntraZonal | Maintenance | 2018-06-22 08:00 | 2018-06-22 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800267 | --- | Substation | IntraZonal | Maintenance | 2018-06-20 08:00 | 2018-06-20 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800293 | --- | Substation | IntraZonal | Upgrading | 2018-10-05 08:00 | 2018-10-05 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800294 | --- | Substation | IntraZonal | Upgrading | 2018-10-08 08:00 | 2018-10-09 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800295 | --- | Substation | IntraZonal | Upgrading | 2018-10-10 08:00 | 2018-10-12 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800297 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-15 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800298 | --- | AC Link | IntraZonal | Upgrading | 2018-04-23 07:30 | 2018-04-28 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201800298 | --- | AC Link | IntraZonal | Upgrading | 2018-04-23 07:30 | 2018-04-28 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 06:59 | Working days |  |  | 23:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201800300 | --- | Substation | IntraZonal | Upgrading | 2018-10-03 08:00 | 2018-10-04 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800325 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-25 08:00 | 2018-06-26 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800329 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-28 08:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 09/03/2018 17:00 v.1 - 07/03/2018 18:00
CA-201800329 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-28 08:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 09/03/2018 17:00 v.1 - 07/03/2018 18:00
CA-201800329 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-28 08:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 09/03/2018 17:00 v.1 - 07/03/2018 18:00
CA-201800329 | --- | AC Link | IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-28 08:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 09/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701765 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-06 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701796 | --- --- | AC Link Substation | CrossZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-11 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Updated | v.2 - 19/03/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701796 | --- --- | AC Link Substation | CrossZonal IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-11 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Updated | v.2 - 19/03/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701797 | --- --- --- --- --- | Substation AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-03 08:00 | 2018-08-12 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/03/2018 16:00
CC-201701797 | --- --- --- --- --- | Substation AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-03 08:00 | 2018-08-12 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/03/2018 16:00
CC-201701810 | --- | AC Link | IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-22 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 08/03/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701810 | --- | AC Link | IntraZonal | Upgrading | 2018-04-03 08:00 | 2018-04-22 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 08/03/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-13 08:00 | 2018-04-30 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 22/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-13 08:00 | 2018-04-30 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 22/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-13 08:00 | 2018-04-30 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 22/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701814 | --- --- --- --- --- | AC Link AC Link Substation AC Link AC Link | CrossZonal CrossZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2018-04-13 08:00 | 2018-04-30 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 22/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701816 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-05 08:00 | 2018-05-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 28/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701816 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-05-05 08:00 | 2018-05-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 28/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701827 | --- --- --- | Substation Substation Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-21 08:00 | 2018-05-25 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701828 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701829 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701829 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701829 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701829 | --- --- --- --- --- --- --- --- --- --- --- --- | Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701834 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701835 | --- --- --- --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-10-01 08:00 | 2018-10-31 17:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 08/03/2018 18:00
CC-201701837 | --- | AC Link | IntraZonal | Maintenance | 2018-05-24 08:00 | 2018-05-28 17:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Updated | v.2 - 28/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701837 | --- | AC Link | IntraZonal | Maintenance | 2018-05-24 08:00 | 2018-05-28 17:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Updated | v.2 - 28/03/2018 17:00 v.1 - 07/03/2018 18:00
CC-201701839 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-04 08:00 | 2018-06-10 16:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 09/03/2018 17:00
CC-201701839 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-04 08:00 | 2018-06-10 16:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 09/03/2018 17:00
CC-201701840 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-07-08 08:00 | 2018-07-08 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701842 | --- --- --- --- --- --- --- --- | Substation Substation Substation Substation AC Link Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-25 08:00 | 2018-06-29 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 30/03/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701858 | --- | Substation | IntraZonal | Upgrading | 2018-08-26 08:00 | 2018-08-26 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701859 | --- | AC Link | IntraZonal | Upgrading | 2018-08-27 08:00 | 2018-08-27 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701862 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-07 08:00 | 2018-09-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 20/03/2018 18:00
CC-201701862 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-07 08:00 | 2018-09-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 20/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/03/2018 18:00
CC-201701864 | --- --- --- --- | AC Link Substation AC Link Substation | CrossZonal IntraZonal CrossZonal IntraZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701864 | --- --- --- --- | AC Link Substation AC Link Substation | CrossZonal IntraZonal CrossZonal IntraZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701870 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-12 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701871 | --- | AC Link | IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701976 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-07 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | ROSN | SICI | Look Up | 700 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201800171 | --- --- --- --- --- | Substation Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-05-03 08:00 | 2018-05-11 16:00 | SICI | ROSN | Look Up | 700 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201800379 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-14 08:00 | 2018-04-14 13:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 13:00 | Working days |  |  | 08:00 - 13:00 | Planned | v.1 - 14/03/2018 17:00
CC-201800379 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-14 08:00 | 2018-04-14 13:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 08:00 till 13:00 | Working days |  |  | 08:00 - 13:00 | Planned | v.1 - 14/03/2018 17:00
CC-201800379 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-14 08:00 | 2018-04-14 13:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 08:00 till 13:00 | Working days |  |  | 08:00 - 13:00 | Planned | v.1 - 14/03/2018 17:00
CC-201800379 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-14 08:00 | 2018-04-14 13:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 08:00 till 13:00 | Working days |  |  | 08:00 - 13:00 | Planned | v.1 - 14/03/2018 17:00
CC-201800404 | --- | AC Link | IntraZonal | Maintenance | 2018-04-12 08:00 | 2018-04-12 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 20/03/2018 18:00
CC-201800405 | --- | Substation | IntraZonal | Maintenance | 2018-04-17 08:00 | 2018-04-17 15:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 20/03/2018 18:00
CC-201800406 | --- | Substation | IntraZonal | Maintenance | 2018-04-17 08:00 | 2018-04-17 15:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 20/03/2018 18:00
CC-201800410 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-16 09:00 | 2018-04-19 14:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 09:00 till 14:00 | Working days |  |  | 09:00 - 14:00 | Planned | v.1 - 22/03/2018 17:00
CC-201800415 | --- | AC Link | CrossZonal | Upgrading | 2018-05-02 08:00 | 2018-05-06 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 22/03/2018 17:00
CC-201800415 | --- | AC Link | CrossZonal | Upgrading | 2018-05-02 08:00 | 2018-05-06 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 22/03/2018 17:00
CC-201800415 | --- | AC Link | CrossZonal | Upgrading | 2018-05-02 08:00 | 2018-05-06 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 22/03/2018 17:00
CC-201800415 | --- | AC Link | CrossZonal | Upgrading | 2018-05-02 08:00 | 2018-05-06 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 22/03/2018 17:00
CC-201800419 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-04-23 09:00 | 2018-04-24 14:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 09:00 till 14:00 | Working days |  |  | 09:00 - 14:00 | Updated | v.2 - 04/04/2018 18:00 v.1 - 22/03/2018 17:00
CC-201800450 | --- | AC Link | CrossZonal | Upgrading | 2018-05-29 08:00 | 2018-05-31 18:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/03/2018 16:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-10 08:00 | 2018-11-11 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 30/03/2018 16:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-10 08:00 | 2018-11-11 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 30/03/2018 16:00
CC-201800468 | --- | Substation | IntraZonal | Maintenance | 2018-04-26 09:00 | 2018-04-27 14:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 09:00 till 14:00 | Working days |  |  | 09:00 - 14:00 | Planned | v.1 - 04/04/2018 18:00
CC-201800487 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2018-05-10 09:00 | 2018-05-11 14:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 06/04/2018 18:00
CC-201800488 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-10-21 08:00 | 2018-10-21 18:00 | CSUD | CNOR | Look Up | 1000 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 06/04/2018 18:00
CC-201800501 | --- | AC Link | CrossZonal | Upgrading | 2018-04-11 06:00 | 2018-04-11 08:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 06:00 till 08:00 | Working days |  |  | 06:00 - 08:00 | Planned | v.1 - 10/04/2018 18:00
PA-201701893 | --- --- | Transformer Transformer | IntraZonal IntraZonal | Maintenance | 2018-04-09 08:00 | 2018-04-12 15:30 | ROSN | SICI | Look Up | 900 | Valid on Working days from 08:00 till 15:30 | Working days |  |  | 08:00 - 15:30 | Planned | v.1 - 03/04/2018 17:00
PA-201701893 | --- --- | Transformer Transformer | IntraZonal IntraZonal | Maintenance | 2018-04-09 08:00 | 2018-04-12 15:30 | SICI | ROSN | Look Up | 900 | Valid on Working days from 08:00 till 15:30 | Working days |  |  | 08:00 - 15:30 | Planned | v.1 - 03/04/2018 17:00