## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 15/06/2018 until 31/12/2018 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 15-06-2018
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 31/05/2018 16:00 v.1 - 07/03/2018 18:00 v.2 - 30/05/2018 17:21
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 31/05/2018 16:00 v.1 - 07/03/2018 18:00 v.2 - 30/05/2018 17:21
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 31/05/2018 16:00 v.1 - 07/03/2018 18:00 v.2 - 30/05/2018 17:21
CA-201701251 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-01 16:00 | 2018-06-15 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 31/05/2018 16:00 v.1 - 07/03/2018 18:00 v.2 - 30/05/2018 17:21
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CNOR | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | CNOR | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701259 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-17 08:00 | 2018-10-05 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701260 | --- --- --- --- --- --- --- | DC Link DC Link DC Link DC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-10-05 16:00 | 2018-10-12 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701262 | --- | AC Link | IntraZonal | Upgrading | 2018-11-28 07:30 | 2018-11-28 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 65 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701263 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 16:30 | 2018-11-12 16:30 | SARD | COAC | Look Up | 80 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 45 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-24 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CA-201800256 | --- | AC Link | IntraZonal | Maintenance | 2018-06-21 08:00 | 2018-06-21 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800257 | --- | Substation | IntraZonal | Maintenance | 2018-06-22 08:00 | 2018-06-22 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800267 | --- | Substation | IntraZonal | Maintenance | 2018-06-20 08:00 | 2018-06-20 16:00 | SARD | COAC | Look Up | 20 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800293 | --- | Substation | IntraZonal | Upgrading | 2018-10-05 08:00 | 2018-10-05 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800294 | --- | Substation | IntraZonal | Upgrading | 2018-10-08 08:00 | 2018-10-09 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800295 | --- | Substation | IntraZonal | Upgrading | 2018-10-10 08:00 | 2018-10-12 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800297 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-10-15 08:00 | 2018-10-15 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800300 | --- | Substation | IntraZonal | Upgrading | 2018-10-03 08:00 | 2018-10-04 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800325 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-25 08:00 | 2018-06-26 16:00 | SARD | COAC | Look Up | 70 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CA-201800558 | --- | AC Link | IntraZonal | Upgrading | 2018-06-25 06:00 | 2018-06-29 14:00 | CORS | SARD | Look Up | 175 | Valid on Working days from 06:00 till 14:00 | Working days |  |  | 06:00 - 14:00 | Planned | v.1 - 20/04/2018 18:00
CA-201800559 | --- | AC Link | IntraZonal | Upgrading | 2018-07-16 06:00 | 2018-07-20 14:00 | CORS | SARD | Look Up | 175 | Valid on Working days from 06:00 till 14:00 | Working days |  |  | 06:00 - 14:00 | Planned | v.1 - 10/05/2018 19:00
CA-201800560 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-07-23 06:00 | 2018-07-27 14:00 | CORS | SARD | Look Up | 175 | Valid on Working days from 06:00 till 14:00 | Working days |  |  | 06:00 - 14:00 | Planned | v.1 - 10/05/2018 19:00
CA-201800694 | --- | AC Link | IntraZonal | Upgrading | 2018-10-08 07:30 | 2018-10-12 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/05/2018 16:00
CA-201800697 | --- | AC Link | IntraZonal | Upgrading | 2018-10-15 07:30 | 2018-10-19 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/05/2018 16:00
CA-201800802 | --- | DC Link | IntraZonal | Forced outage | 2018-06-07 | 2018-06-30 23:59 | CNOR | CORS | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.3 - 08/06/2018 17:00 v.2 - 07/06/2018 17:00 v.1 - 06/06/2018 18:00
CA-201800802 | --- | DC Link | IntraZonal | Forced outage | 2018-06-07 | 2018-06-30 23:59 | CNOR | CORS | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.3 - 08/06/2018 17:00 v.2 - 07/06/2018 17:00 v.1 - 06/06/2018 18:00
CA-201800802 | --- | DC Link | IntraZonal | Forced outage | 2018-06-07 | 2018-06-30 23:59 | CORS | CNOR | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.3 - 08/06/2018 17:00 v.2 - 07/06/2018 17:00 v.1 - 06/06/2018 18:00
CA-201800802 | --- | DC Link | IntraZonal | Forced outage | 2018-06-07 | 2018-06-30 23:59 | CORS | CNOR | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.3 - 08/06/2018 17:00 v.2 - 07/06/2018 17:00 v.1 - 06/06/2018 18:00
CA-201800808 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-18 07:30 | 2018-06-18 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 08/06/2018 17:00
CA-201800808 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-18 07:30 | 2018-06-18 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 08/06/2018 17:00
CA-201800808 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-18 07:30 | 2018-06-18 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 08/06/2018 17:00
CA-201800808 | --- --- --- --- | DC Link DC Link DC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-06-18 07:30 | 2018-06-18 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 08/06/2018 17:00
CA-201800843 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-15 20:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 16:00 till 20:00 | Working days |  |  | 16:00 - 20:00 | Planned | v.1 - 13/06/2018 18:00
CA-201800843 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-15 20:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 16:00 till 20:00 | Working days |  |  | 16:00 - 20:00 | Planned | v.1 - 13/06/2018 18:00
CA-201800843 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-15 20:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 16:00 till 20:00 | Working days |  |  | 16:00 - 20:00 | Planned | v.1 - 13/06/2018 18:00
CA-201800843 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-15 20:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 16:00 till 20:00 | Working days |  |  | 16:00 - 20:00 | Planned | v.1 - 13/06/2018 18:00
CA-201800844 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-29 16:00 | CNOR | CORS | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 13/06/2018 18:00
CA-201800844 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-29 16:00 | CNOR | CORS | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 13/06/2018 18:00
CA-201800844 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-29 16:00 | CORS | CNOR | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 13/06/2018 18:00
CA-201800844 | --- | DC Link | IntraZonal | Maintenance | 2018-06-15 16:00 | 2018-06-29 16:00 | CORS | CNOR | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 13/06/2018 18:00
CC-201701765 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-06 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701797 | --- --- --- --- --- | Substation AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-03 08:00 | 2018-08-12 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/03/2018 16:00
CC-201701797 | --- --- --- --- --- | Substation AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-08-03 08:00 | 2018-08-12 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/03/2018 16:00
CC-201701826 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 08:00 | 2018-09-20 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701826 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 08:00 | 2018-09-20 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701831 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701833 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2018-09-09 08:00 | 2018-09-17 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701834 | --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2018-10-04 08:00 | 2018-10-05 17:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 31/05/2018 16:00
CC-201701835 | --- --- --- --- --- --- | AC Link AC Link AC Link Substation AC Link AC Link | CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal | Upgrading | 2018-10-04 08:00 | 2018-10-05 17:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 31/05/2018 16:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-21 08:00 | 2018-09-30 16:00 | ROSN | SUD | Look Up | 550 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-21 08:00 | 2018-09-30 16:00 | ROSN | SUD | Look Up | 550 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-21 08:00 | 2018-09-30 16:00 | SUD | CSUD | Look Up | 2800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701838 | --- --- --- | Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-21 08:00 | 2018-09-30 16:00 | SUD | CSUD | Look Up | 2800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 13/04/2018 17:00
CC-201701840 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-07-08 08:00 | 2018-07-08 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701842 | --- --- --- --- --- | Substation AC Link Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-06-25 08:00 | 2018-06-29 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 30/03/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701843 | --- --- --- | AC Link AC Link Substation | CrossZonal IntraZonal IntraZonal | Upgrading | 2018-08-05 08:00 | 2018-08-05 18:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Cancelled | v.2 - 06/04/2018 18:00 v.1 - 07/03/2018 18:00
CC-201701845 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701845 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-08-20 08:00 | 2018-08-24 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CNOR | NORD | Look Up | 900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701846 | --- --- --- --- --- --- --- | AC Link AC Link AC Link Substation Substation Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-10-15 08:00 | 2018-10-30 16:00 | NORD | CNOR | Look Up | 2000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701855 | --- | Substation | IntraZonal | Upgrading | 2018-08-25 08:00 | 2018-08-25 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701858 | --- | Substation | IntraZonal | Upgrading | 2018-08-26 08:00 | 2018-08-26 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701859 | --- | AC Link | IntraZonal | Upgrading | 2018-08-27 08:00 | 2018-08-27 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701862 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-07 08:00 | 2018-09-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 20/03/2018 18:00
CC-201701862 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2018-09-07 08:00 | 2018-09-11 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 20/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701863 | --- | AC Link | IntraZonal | Upgrading | 2018-09-12 07:00 | 2018-09-18 16:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:39 | Holidays |  |  | 00:00 - 23:39 | Planned | v.1 - 07/03/2018 18:00
CC-201701864 | --- --- --- --- | AC Link Substation AC Link Substation | CrossZonal IntraZonal CrossZonal IntraZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701864 | --- --- --- --- | AC Link Substation AC Link Substation | CrossZonal IntraZonal CrossZonal IntraZonal | Upgrading | 2018-10-01 08:00 | 2018-10-13 17:00 | SUD | CSUD | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701865 | --- --- | AC Link Substation | IntraZonal IntraZonal | Upgrading | 2018-11-01 08:00 | 2018-11-04 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701868 | --- --- --- --- | Substation AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-05 08:00 | 2018-11-09 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701869 | --- | AC Link | IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701870 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-12 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701871 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/03/2018 18:00
CC-201701976 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-09-03 08:00 | 2018-09-07 16:00 | SUD | CSUD | Look Up | 4500 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Updated | v.2 - 01/06/2018 16:00 v.1 - 30/03/2018 16:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Updated | v.2 - 01/06/2018 16:00 v.1 - 30/03/2018 16:00
CC-201800488 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-10-21 08:00 | 2018-10-21 18:00 | CSUD | CNOR | Look Up | 1000 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 06/04/2018 18:00
CC-201800608 | --- | AC Link | CrossZonal | Upgrading | 2018-06-20 08:00 | 2018-06-24 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800608 | --- | AC Link | CrossZonal | Upgrading | 2018-06-20 08:00 | 2018-06-24 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800608 | --- | AC Link | CrossZonal | Upgrading | 2018-06-20 08:00 | 2018-06-24 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800608 | --- | AC Link | CrossZonal | Upgrading | 2018-06-20 08:00 | 2018-06-24 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800609 | --- | AC Link | CrossZonal | Upgrading | 2018-06-15 08:00 | 2018-06-19 15:00 | ROSN | SUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800609 | --- | AC Link | CrossZonal | Upgrading | 2018-06-15 08:00 | 2018-06-19 15:00 | ROSN | SUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800609 | --- | AC Link | CrossZonal | Upgrading | 2018-06-15 08:00 | 2018-06-19 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800609 | --- | AC Link | CrossZonal | Upgrading | 2018-06-15 08:00 | 2018-06-19 15:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 11/05/2018 16:00
CC-201800702 | --- | DC Link | CrossZonal | Maintenance | 2018-05-21 08:00 | 2018-06-28 16:00 | BRNN | GREC | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/06/2018 16:00 v.1 - 18/05/2018 16:00
CC-201800702 | --- | DC Link | CrossZonal | Maintenance | 2018-05-21 08:00 | 2018-06-28 16:00 | BRNN | GREC | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/06/2018 16:00 v.1 - 18/05/2018 16:00
CC-201800702 | --- | DC Link | CrossZonal | Maintenance | 2018-05-21 08:00 | 2018-06-28 16:00 | GREC | BRNN | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/06/2018 16:00 v.1 - 18/05/2018 16:00
CC-201800702 | --- | DC Link | CrossZonal | Maintenance | 2018-05-21 08:00 | 2018-06-28 16:00 | GREC | BRNN | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/06/2018 16:00 v.1 - 18/05/2018 16:00
CC-201800785 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Maintenance | 2018-10-06 08:00 | 2018-10-10 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 01/06/2018 16:00
CC-201800785 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Maintenance | 2018-10-06 08:00 | 2018-10-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 01/06/2018 16:00
CC-201800786 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Maintenance | 2018-10-06 08:00 | 2018-10-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 01/06/2018 16:00
CC-201800786 | --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link | CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal CrossZonal | Maintenance | 2018-10-06 08:00 | 2018-10-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 01/06/2018 16:00
CC-201800817 | --- | AC Link | IntraZonal | Maintenance | 2018-06-15 08:00 | 2018-06-15 16:00 | ROSN | SUD | Look Up | 2250 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 11/06/2018 17:00
CC-201800831 | --- | Substation | IntraZonal | Maintenance | 2018-06-30 08:00 | 2018-07-01 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 12/06/2018 17:00
CC-201800831 | --- | Substation | IntraZonal | Maintenance | 2018-06-30 08:00 | 2018-07-01 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 12/06/2018 17:00
CC-201800834 | --- | AC Link | IntraZonal | Other | 2018-07-01 08:00 | 2018-07-01 15:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 15:00 | Holidays |  |  | 08:00 - 15:00 | Planned | v.1 - 12/06/2018 17:00