## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 18/11/2018 until 31/12/2018 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 18-11-2018
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 11/10/2018 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 11/10/2018 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 55 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 11/10/2018 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 11/10/2018 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 45 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 11/10/2018 17:00
CA-201701550 | --- | AC Link | IntraZonal | Upgrading | 2018-11-13 07:30 | 2018-11-27 16:30 | SARD | COAC | Look Up | 55 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 11/10/2018 17:00
CA-201801086 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-30 08:00 | 2018-11-30 16:30 | SARD | COAC | Look Up | 35 | Valid on Working days from 08:00 till 16:30 | Working days |  |  | 08:00 - 16:30 | Planned | v.1 - 25/09/2018 17:00
CA-201801679 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-11-29 08:00 | 2018-11-29 16:00 | SARD | COAC | Look Up | 65 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 14/11/2018 16:00
CA-201801777 | --- --- --- --- --- --- --- | DC Link DC Link DC Link AC Link AC Link AC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 07:30 | 2018-11-23 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 15/11/2018 17:00
CA-201801777 | --- --- --- --- --- --- --- | DC Link DC Link DC Link AC Link AC Link AC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 07:30 | 2018-11-23 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 15/11/2018 17:00
CA-201801777 | --- --- --- --- --- --- --- | DC Link DC Link DC Link AC Link AC Link AC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 07:30 | 2018-11-23 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 15/11/2018 17:00
CA-201801777 | --- --- --- --- --- --- --- | DC Link DC Link DC Link AC Link AC Link AC Link DC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 07:30 | 2018-11-23 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 15/11/2018 17:00
CA-201801804 | --- | AC Link | IntraZonal | Forced outage | 2018-11-17 06:30 | 2018-11-17 17:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 06:30 till 17:00 | Working days |  |  | 06:30 - 17:00 | Updated | v.2 - 14/11/2018 16:00 v.1 - 13/11/2018 18:00
CA-201801804 | --- | AC Link | IntraZonal | Forced outage | 2018-11-17 06:30 | 2018-11-17 17:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 06:30 till 17:00 | Working days |  |  | 06:30 - 17:00 | Updated | v.2 - 14/11/2018 16:00 v.1 - 13/11/2018 18:00
CA-201801814 | --- | AC Link | IntraZonal | Upgrading | 2018-12-10 07:30 | 2018-12-14 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/11/2018 16:00
CC-201701861 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-23 18:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 27/08/2018 17:00 v.1 - 17/08/2018 16:00
CC-201701865 | --- --- --- --- | AC Link Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 17/08/2018 16:00
CC-201701865 | --- --- --- --- | AC Link Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-12-02 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 17/08/2018 16:00
CC-201701869 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 31/10/2018 19:00 v.1 - 07/03/2018 18:00
CC-201701869 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2018-11-05 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 31/10/2018 19:00 v.1 - 07/03/2018 18:00
CC-201701870 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2018-11-12 08:00 | 2018-11-16 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 07/03/2018 18:00
CC-201701871 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2018-11-20 08:00 | 2018-11-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 07/11/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 08:00 | 2018-11-30 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 30/07/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 08:00 | 2018-11-30 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 30/07/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 08:00 | 2018-11-30 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 30/07/2018 16:00 v.1 - 07/03/2018 18:00
CC-201701872 | --- --- --- --- --- --- --- --- --- --- | Substation AC Link Substation Substation Substation AC Link AC Link AC Link Substation Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2018-11-21 08:00 | 2018-11-30 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 30/07/2018 16:00 v.1 - 07/03/2018 18:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Updated | v.2 - 01/06/2018 16:00 v.1 - 30/03/2018 16:00
CC-201800453 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 17:00 | CSUD | CNOR | Look Up | 2200 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Updated | v.2 - 01/06/2018 16:00 v.1 - 30/03/2018 16:00
CC-201801137 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-11-25 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 17/08/2018 16:00 v.1 - 30/07/2018 16:00
CC-201801137 | --- --- | Substation AC Link | IntraZonal IntraZonal | Upgrading | 2018-11-24 08:00 | 2018-11-25 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 17/08/2018 16:00 v.1 - 30/07/2018 16:00
CC-201801234 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal CrossZonal | Upgrading | 2018-12-01 08:00 | 2018-12-02 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 25/10/2018 16:00 v.1 - 27/08/2018 17:00
CC-201801234 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal CrossZonal | Upgrading | 2018-12-01 08:00 | 2018-12-02 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 25/10/2018 16:00 v.1 - 27/08/2018 17:00
CC-201801234 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal CrossZonal | Upgrading | 2018-12-01 08:00 | 2018-12-02 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 25/10/2018 16:00 v.1 - 27/08/2018 17:00
CC-201801234 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal CrossZonal | Upgrading | 2018-12-01 08:00 | 2018-12-02 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 25/10/2018 16:00 v.1 - 27/08/2018 17:00
CC-201801286 | --- | DC Link | CrossZonal | Forced outage | 2018-09-04 | 2018-11-30 23:59 | BRNN | GREC | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 13/11/2018 10:00 v.4 - 26/10/2018 18:00 v.3 - 05/10/2018 17:00 v.2 - 20/09/2018 17:00 v.1 - 03/09/2018 14:00
CC-201801286 | --- | DC Link | CrossZonal | Forced outage | 2018-09-04 | 2018-11-30 23:59 | BRNN | GREC | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 13/11/2018 10:00 v.4 - 26/10/2018 18:00 v.3 - 05/10/2018 17:00 v.2 - 20/09/2018 17:00 v.1 - 03/09/2018 14:00
CC-201801286 | --- | DC Link | CrossZonal | Forced outage | 2018-09-04 | 2018-11-30 23:59 | GREC | BRNN | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 13/11/2018 10:00 v.4 - 26/10/2018 18:00 v.3 - 05/10/2018 17:00 v.2 - 20/09/2018 17:00 v.1 - 03/09/2018 14:00
CC-201801286 | --- | DC Link | CrossZonal | Forced outage | 2018-09-04 | 2018-11-30 23:59 | GREC | BRNN | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 13/11/2018 10:00 v.4 - 26/10/2018 18:00 v.3 - 05/10/2018 17:00 v.2 - 20/09/2018 17:00 v.1 - 03/09/2018 14:00
CC-201801622 | --- --- | Substation AC Link | IntraZonal CrossZonal | Maintenance | 2018-12-17 08:00 | 2018-12-21 16:00 | CNOR | NORD | Look Up | 1400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 17/10/2018 18:00
CC-201801622 | --- --- | Substation AC Link | IntraZonal CrossZonal | Maintenance | 2018-12-17 08:00 | 2018-12-21 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 17/10/2018 18:00
CC-201801697 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 15:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Updated | v.2 - 06/11/2018 18:00 v.1 - 31/10/2018 19:00
CC-201801697 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2018-11-17 08:00 | 2018-11-18 15:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 15:00 | Holidays |  |  | 08:00 - 15:00 | Updated | v.2 - 06/11/2018 18:00 v.1 - 31/10/2018 19:00
CC-201801744 | --- | Substation | IntraZonal | Maintenance | 2018-11-26 08:00 | 2018-11-26 16:00 | SUD | CSUD | Look Up | 3800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 15/11/2018 17:00 v.1 - 07/11/2018 16:00
CC-201801847 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2018-11-18 09:00 | 2018-11-18 15:00 | SUD | CSUD | Look Up | 3800 | Valid on Holidays from 09:00 till 15:00 | Holidays |  |  | 09:00 - 15:00 | Planned | v.1 - 16/11/2018 18:00
PA-201801704 | --- | Substation | IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-21 16:00 | ROSN | SICI | Look Up | 750 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 06/11/2018 18:00
PA-201801704 | --- | Substation | IntraZonal | Maintenance | 2018-11-19 08:00 | 2018-11-21 16:00 | SICI | ROSN | Look Up | 750 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 06/11/2018 18:00
IG-201800016 | --- | DC Link | CrossZonal | Forced outage | 2018-11-18 04:31 | 2018-11-19 12:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.1 -18/11/2018 06:00 v.2 -18/11/2018 15:30
IG-201800016 | --- | DC Link | CrossZonal | Forced outage | 2018-11-18 04:31 | 2018-11-19 12:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.1 -18/11/2018 06:00 v.2 -18/11/2018 15:30