## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 19/03/2019 until 31/12/2019 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 19-03-2019
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201801307 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-05-30 16:00 | CSUD | SARD | Look Up | 210 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CA-201801307 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-05-30 16:00 | SARD | CSUD | Look Up | 720 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CA-201801316 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 07:30 | 2019-10-05 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801317 | --- | AC Link | IntraZonal | Upgrading | 2019-10-07 07:30 | 2019-10-12 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801318 | --- | AC Link | IntraZonal | Upgrading | 2019-10-14 07:30 | 2019-10-19 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801319 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801320 | --- | AC Link | IntraZonal | Upgrading | 2019-10-28 07:30 | 2019-11-02 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801326 | --- | AC Link | IntraZonal | Upgrading | 2019-06-17 07:30 | 2019-06-21 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801327 | --- | AC Link | IntraZonal | Upgrading | 2019-06-24 07:30 | 2019-06-28 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801329 | --- | AC Link | IntraZonal | Upgrading | 2019-05-27 07:30 | 2019-05-31 16:30 | SARD | COAC | Look Up | 20 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801330 | --- | AC Link | IntraZonal | Upgrading | 2019-06-03 07:30 | 2019-06-07 16:30 | SARD | COAC | Look Up | 20 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801332 | --- | AC Link | IntraZonal | Upgrading | 2019-10-07 07:30 | 2019-10-11 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801333 | --- | AC Link | IntraZonal | Upgrading | 2019-10-14 07:30 | 2019-10-18 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801335 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-09-08 08:00 | 2019-09-08 12:00 | SARD | COAC | Look Up | 0 | Valid on Working days from 08:00 till 12:00 | Working days |  |  | 08:00 - 12:00 | Planned | v.1 - 25/02/2019 18:00
CA-201801337 | --- | AC Link | IntraZonal | Upgrading | 2019-03-18 07:30 | 2019-03-22 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801339 | --- | AC Link | IntraZonal | Upgrading | 2019-03-25 07:30 | 2019-03-29 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801340 | --- | AC Link | IntraZonal | Upgrading | 2019-04-01 07:30 | 2019-04-05 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801341 | --- | AC Link | IntraZonal | Upgrading | 2019-04-08 07:30 | 2019-04-12 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801342 | --- | AC Link | IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-14 17:00 | SARD | COAC | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801342 | --- | AC Link | IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-14 17:00 | SARD | COAC | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801350 | --- | AC Link | IntraZonal | Upgrading | 2019-04-15 07:30 | 2019-04-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801352 | --- | AC Link | IntraZonal | Upgrading | 2019-04-23 07:30 | 2019-04-27 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801353 | --- | AC Link | IntraZonal | Upgrading | 2019-04-29 07:30 | 2019-05-03 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801354 | --- | AC Link | IntraZonal | Upgrading | 2019-05-06 07:30 | 2019-05-10 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801359 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-01 08:00 | 2019-07-05 16:00 | CSUD | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801359 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-01 08:00 | 2019-07-05 16:00 | CSUD | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801359 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-01 08:00 | 2019-07-05 16:00 | SARD | CSUD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801359 | --- --- --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-01 08:00 | 2019-07-05 16:00 | SARD | CSUD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801360 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801360 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801360 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801360 | --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801365 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801365 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801365 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801365 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CNOR | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | CNOR | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801366 | --- --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801373 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-11-21 08:00 | 2019-11-21 17:00 | SARD | COAC | Look Up | 35 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 25/02/2019 18:00
CA-201801374 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-11-22 08:00 | 2019-11-22 17:00 | SARD | COAC | Look Up | 40 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 25/02/2019 18:00
CA-201801886 | --- | Substation | IntraZonal | Maintenance | 2019-06-24 08:00 | 2019-06-28 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801886 | --- | Substation | IntraZonal | Maintenance | 2019-06-24 08:00 | 2019-06-28 16:00 | CSUD | SARD | Look Up | 690 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CA-201801930 | --- --- | AC Link Substation | IntraZonal IntraZonal | Maintenance | 2019-07-01 08:00 | 2019-07-04 16:00 | SARD | COAC | Look Up | 35 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CA-201900018 | --- | DC Link | CrossZonal | Forced outage | 2019-01-04 | 2019-03-23 23:59 | CNOR | CORS | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 15/03/2019 12:00 v.4 - 13/03/2019 10:00 v.3 - 06/03/2019 10:00 v.2 - 27/02/2019 18:00 v.1 - 25/02/2019 18:00
CA-201900018 | --- | DC Link | CrossZonal | Forced outage | 2019-01-04 | 2019-03-23 23:59 | CNOR | CORS | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 15/03/2019 12:00 v.4 - 13/03/2019 10:00 v.3 - 06/03/2019 10:00 v.2 - 27/02/2019 18:00 v.1 - 25/02/2019 18:00
CA-201900018 | --- | DC Link | CrossZonal | Forced outage | 2019-01-04 | 2019-03-23 23:59 | CORS | CNOR | Look Up | 150 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 15/03/2019 12:00 v.4 - 13/03/2019 10:00 v.3 - 06/03/2019 10:00 v.2 - 27/02/2019 18:00 v.1 - 25/02/2019 18:00
CA-201900018 | --- | DC Link | CrossZonal | Forced outage | 2019-01-04 | 2019-03-23 23:59 | CORS | CNOR | Look Up | 150 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.5 - 15/03/2019 12:00 v.4 - 13/03/2019 10:00 v.3 - 06/03/2019 10:00 v.2 - 27/02/2019 18:00 v.1 - 25/02/2019 18:00
CA-201900214 | --- --- --- --- | AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-03-23 08:00 | 2019-03-23 17:00 | SARD | COAC | Look Up | 40 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Cancelled | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CA-201900253 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2019-03-19 08:00 | 2019-03-20 17:00 | SARD | COAC | Look Up | 95 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 06/03/2019 18:00
CA-201900253 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2019-03-19 08:00 | 2019-03-20 17:00 | SARD | COAC | Look Up | 90 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 06/03/2019 18:00
CA-201900253 | --- --- | Substation AC Link | IntraZonal IntraZonal | Maintenance | 2019-03-19 08:00 | 2019-03-20 17:00 | SARD | COAC | Look Up | 95 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 06/03/2019 18:00
CA-201900264 | --- | Substation | IntraZonal | Maintenance | 2019-03-26 08:00 | 2019-03-26 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201900265 | --- | AC Link | IntraZonal | Upgrading | 2019-04-15 07:30 | 2019-04-19 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 25/02/2019 18:00
CA-201900463 | --- --- | DC Link DC Link | IntraZonal IntraZonal | Other | 2019-03-25 07:00 | 2019-03-25 10:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 07:00 till 10:00 | Working days |  |  | 07:00 - 10:00 | Cancelled | v.2 - 14/03/2019 18:00 v.1 - 13/03/2019 10:00
CA-201900463 | --- --- | DC Link DC Link | IntraZonal IntraZonal | Other | 2019-03-25 07:00 | 2019-03-25 10:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 07:00 till 10:00 | Working days |  |  | 07:00 - 10:00 | Cancelled | v.2 - 14/03/2019 18:00 v.1 - 13/03/2019 10:00
CA-201900463 | --- --- | DC Link DC Link | IntraZonal IntraZonal | Other | 2019-03-25 07:00 | 2019-03-25 10:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 07:00 till 10:00 | Working days |  |  | 07:00 - 10:00 | Cancelled | v.2 - 14/03/2019 18:00 v.1 - 13/03/2019 10:00
CA-201900463 | --- --- | DC Link DC Link | IntraZonal IntraZonal | Other | 2019-03-25 07:00 | 2019-03-25 10:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 07:00 till 10:00 | Working days |  |  | 07:00 - 10:00 | Cancelled | v.2 - 14/03/2019 18:00 v.1 - 13/03/2019 10:00
CC-201801926 | --- --- --- --- --- --- --- --- | Substation Substation Substation AC Link AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-03-20 10:00 | 2019-03-23 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.5 - 19/03/2019 15:00 v.4 - 15/03/2019 12:00 v.3 - 08/03/2019 17:00 v.2 - 28/02/2019 17:00 v.1 - 25/02/2019 18:00
CC-201801927 | --- --- --- --- --- --- --- | Substation AC Link AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-23 08:00 | 2019-04-05 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801927 | --- --- --- --- --- --- --- | Substation AC Link AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-23 08:00 | 2019-04-05 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801927 | --- --- --- --- --- --- --- | Substation AC Link AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-23 08:00 | 2019-04-05 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801927 | --- --- --- --- --- --- --- | Substation AC Link AC Link Substation Substation AC Link AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-23 08:00 | 2019-04-05 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801929 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2019-04-06 08:00 | 2019-05-08 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 12/03/2019 18:00
CC-201801929 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal CrossZonal IntraZonal IntraZonal | Upgrading | 2019-04-06 08:00 | 2019-05-08 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 12/03/2019 18:00
CC-201801937 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801937 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801937 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801938 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801939 | --- --- --- | Substation AC Link Substation | IntraZonal CrossZonal IntraZonal | Upgrading | 2019-04-10 08:00 | 2019-04-14 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801939 | --- --- --- | Substation AC Link Substation | IntraZonal CrossZonal IntraZonal | Upgrading | 2019-04-10 08:00 | 2019-04-14 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801940 | --- --- --- | Substation AC Link Substation | IntraZonal CrossZonal IntraZonal | Upgrading | 2019-04-10 08:00 | 2019-04-14 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801940 | --- --- --- | Substation AC Link Substation | IntraZonal CrossZonal IntraZonal | Upgrading | 2019-04-10 08:00 | 2019-04-14 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801941 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801941 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801941 | --- --- --- --- --- | Substation Substation AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-06 16:00 | 2019-05-10 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801944 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801944 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801944 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801944 | --- --- --- | Substation AC Link AC Link | IntraZonal CrossZonal CrossZonal | Upgrading | 2019-05-02 08:00 | 2019-05-06 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801949 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801949 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801949 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801949 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801950 | --- --- --- --- --- | AC Link AC Link Substation Substation AC Link | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CNOR | NORD | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | CSUD | CNOR | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801953 | --- --- --- --- --- --- --- --- --- --- --- | Substation Substation AC Link AC Link Substation Substation Substation Substation Substation Substation Substation | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-09 08:00 | 2019-05-20 18:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Updated | v.2 - 14/03/2019 18:00 v.1 - 25/02/2019 18:00
CC-201801954 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-05-13 08:00 | 2019-05-17 16:00 | SUD | CSUD | Look Up | 4000 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801955 | --- --- --- --- --- --- | AC Link Substation Substation AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2019-05-21 08:00 | 2019-05-31 15:00 | ROSN | SUD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801955 | --- --- --- --- --- --- | AC Link Substation Substation AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2019-05-21 08:00 | 2019-05-31 15:00 | ROSN | SUD | Look Up | 900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801955 | --- --- --- --- --- --- | AC Link Substation Substation AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2019-05-21 08:00 | 2019-05-31 15:00 | SUD | CSUD | Look Up | 3300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801955 | --- --- --- --- --- --- | AC Link Substation Substation AC Link AC Link AC Link | CrossZonal IntraZonal IntraZonal CrossZonal CrossZonal CrossZonal | Upgrading | 2019-05-21 08:00 | 2019-05-31 15:00 | SUD | CSUD | Look Up | 3300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801956 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-06-04 09:00 | 2019-06-15 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801956 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-06-04 09:00 | 2019-06-15 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801956 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-06-04 09:00 | 2019-06-15 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801956 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-06-04 09:00 | 2019-06-15 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801957 | --- | AC Link | IntraZonal | Maintenance | 2019-06-28 09:00 | 2019-07-01 18:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801957 | --- | AC Link | IntraZonal | Maintenance | 2019-06-28 09:00 | 2019-07-01 18:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801958 | --- | AC Link | IntraZonal | Maintenance | 2019-07-21 08:00 | 2019-07-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801958 | --- | AC Link | IntraZonal | Maintenance | 2019-07-21 08:00 | 2019-07-23 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801959 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-03 07:00 | 2019-08-13 17:00 | SUD | CSUD | Look Up | 4000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801959 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-03 07:00 | 2019-08-13 17:00 | SUD | CSUD | Look Up | 4000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801960 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-08-19 08:00 | 2019-09-06 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801960 | --- --- --- | AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-08-19 08:00 | 2019-09-06 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801961 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-27 08:00 | 2019-09-15 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801961 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-27 08:00 | 2019-09-15 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801962 | --- | Substation | IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801962 | --- | Substation | IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801962 | --- | Substation | IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801962 | --- | Substation | IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801963 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-10-04 08:00 | 2019-10-10 17:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 18/03/2019 17:00 v.1 - 25/02/2019 18:00
CC-201801963 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-10-04 08:00 | 2019-10-10 17:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 18/03/2019 17:00 v.1 - 25/02/2019 18:00
CC-201801963 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-10-04 08:00 | 2019-10-10 17:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Cancelled | v.2 - 18/03/2019 17:00 v.1 - 25/02/2019 18:00
CC-201801963 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-10-04 08:00 | 2019-10-10 17:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Cancelled | v.2 - 18/03/2019 17:00 v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201801965 | --- --- --- --- | AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 08:00 | 2019-10-13 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201801965 | --- --- --- --- | AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 08:00 | 2019-10-13 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201802037 | --- --- | DC Link Substation | CrossZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-06-16 16:00 | GREC | SUD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201802037 | --- --- | DC Link Substation | CrossZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-06-16 16:00 | GREC | SUD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201802037 | --- --- | DC Link Substation | CrossZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-06-16 16:00 | SUD | GREC | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201802037 | --- --- | DC Link Substation | CrossZonal IntraZonal | Maintenance | 2019-05-27 08:00 | 2019-06-16 16:00 | SUD | GREC | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201802048 | --- | Substation | IntraZonal | Maintenance | 2019-11-06 09:00 | 2019-11-06 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201802048 | --- | Substation | IntraZonal | Maintenance | 2019-11-06 09:00 | 2019-11-06 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201802113 | --- --- | Substation AC Link | IntraZonal CrossZonal | Maintenance | 2019-11-05 08:00 | 2019-11-06 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201802114 | --- --- | Substation AC Link | IntraZonal CrossZonal | Maintenance | 2019-11-05 08:00 | 2019-11-06 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201900019 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-06-17 08:00 | 2019-06-28 16:00 | CNOR | NORD | Look Up | 1900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900019 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-06-17 08:00 | 2019-06-28 16:00 | CNOR | NORD | Look Up | 1900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900019 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-06-17 08:00 | 2019-06-28 16:00 | NORD | CNOR | Look Up | 2800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900019 | --- --- --- | Substation Substation AC Link | IntraZonal IntraZonal IntraZonal | Maintenance | 2019-06-17 08:00 | 2019-06-28 16:00 | NORD | CNOR | Look Up | 2800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900021 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-06-29 09:00 | 2019-07-05 16:00 | CNOR | NORD | Look Up | 1900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900021 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-06-29 09:00 | 2019-07-05 16:00 | CNOR | NORD | Look Up | 1900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900183 | --- | AC Link | IntraZonal | Maintenance | 2019-04-01 08:00 | 2019-04-05 16:00 | SUD | CSUD | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 25/02/2019 18:00
CC-201900211 | --- --- --- --- --- --- | Substation Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-06 08:00 | 2019-05-10 16:00 | ROSN | SICI | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900211 | --- --- --- --- --- --- | Substation Substation Substation Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-05-06 08:00 | 2019-05-10 16:00 | SICI | ROSN | Look Up | 700 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/02/2019 18:00
CC-201900282 | --- | AC Link | IntraZonal | Maintenance | 2019-06-03 08:00 | 2019-06-05 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 26/02/2019 18:00
CC-201900382 | --- --- | AC Link AC Link | IntraZonal CrossZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/03/2019 18:00
CC-201900382 | --- --- | AC Link AC Link | IntraZonal CrossZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 14/03/2019 18:00
CC-201900382 | --- --- | AC Link AC Link | IntraZonal CrossZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 14/03/2019 18:00
CC-201900382 | --- --- | AC Link AC Link | IntraZonal CrossZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 14/03/2019 18:00
CC-201900432 | --- | AC Link | IntraZonal | Maintenance | 2019-06-10 08:00 | 2019-06-14 15:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 18/03/2019 17:00
CC-201900433 | --- | AC Link | IntraZonal | Maintenance | 2019-06-17 08:00 | 2019-06-19 15:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 18/03/2019 17:00
CC-201900439 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-24 08:00 | 2019-03-31 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/03/2019 17:00
CC-201900439 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-24 08:00 | 2019-03-31 16:00 | ROSN | SUD | Look Up | 1200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 18/03/2019 17:00
CC-201900439 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-24 08:00 | 2019-03-31 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/03/2019 17:00
CC-201900439 | --- --- --- | Substation AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-03-24 08:00 | 2019-03-31 16:00 | SUD | CSUD | Look Up | 3200 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 18/03/2019 17:00
CC-201900486 | --- | AC Link | IntraZonal | Upgrading | 2019-03-14 | 2019-03-20 10:00 | ROSN | SUD | Look Up | 600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 19/03/2019 15:00
CC-201900486 | --- | AC Link | IntraZonal | Upgrading | 2019-03-14 | 2019-03-20 10:00 | ROSN | SUD | Look Up | 600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 19/03/2019 15:00
CC-201900486 | --- | AC Link | IntraZonal | Upgrading | 2019-03-14 | 2019-03-20 10:00 | SUD | CSUD | Look Up | 3000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 19/03/2019 15:00
CC-201900486 | --- | AC Link | IntraZonal | Upgrading | 2019-03-14 | 2019-03-20 10:00 | SUD | CSUD | Look Up | 3000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 19/03/2019 15:00
PA-201900481 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-07 18:00 | ROSN | SICI | Look Up | 750 | Valid on Working days from 08:00 till 18:00 | Working days |  |  | 08:00 - 18:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900481 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-07 18:00 | ROSN | SICI | Look Up | 750 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900481 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-07 18:00 | SICI | ROSN | Look Up | 750 | Valid on Working days from 08:00 till 18:00 | Working days |  |  | 08:00 - 18:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900481 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-04-01 08:00 | 2019-04-07 18:00 | SICI | ROSN | Look Up | 750 | Valid on Holidays from 08:00 till 18:00 | Holidays |  |  | 08:00 - 18:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900492 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-04-08 08:00 | 2019-05-05 17:00 | ROSN | SICI | Look Up | 750 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900492 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-04-08 08:00 | 2019-05-05 17:00 | ROSN | SICI | Look Up | 750 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900492 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-04-08 08:00 | 2019-05-05 17:00 | SICI | ROSN | Look Up | 750 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 19/03/2019 15:00
PA-201900492 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-04-08 08:00 | 2019-05-05 17:00 | SICI | ROSN | Look Up | 750 | Valid on Holidays from 08:00 till 17:00 | Holidays |  |  | 08:00 - 17:00 | Planned | v.1 - 19/03/2019 15:00