## scambi_zone_pub_od_gio
Transmission Asset unavailability | From 09/07/2019 until 31/12/2019 - Unavailability terminated are not present in the report, publications before 15/09/2016 are available at the link http://www.terna.it/it-it/sistemaelettrico/transparencyreport/transmissionandinterconnection/plannedoutages.aspx -
Created 09-07-2019
ID Unavailability | Affected asset | Type of asset | Location | Reason | Event start | estimated event stop | Bidding zone FROM | Bidding zone TO | Uncostrained limit | New limit | Comments | Type of day | Custom period start | Custom period end | Limit time slot | Status of unavailability | History of prior publications regarding the same event
CA-201801316 | --- --- --- | AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 07:30 | 2019-10-05 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801317 | --- | AC Link | IntraZonal | Upgrading | 2019-10-07 07:30 | 2019-10-12 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801318 | --- | AC Link | IntraZonal | Upgrading | 2019-10-14 07:30 | 2019-10-19 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801319 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801320 | --- | AC Link | IntraZonal | Upgrading | 2019-10-28 07:30 | 2019-11-02 16:30 | CORS | SARD | Look Up | 175 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801332 | --- | AC Link | IntraZonal | Upgrading | 2019-10-07 07:30 | 2019-10-11 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801333 | --- | AC Link | IntraZonal | Upgrading | 2019-10-14 07:30 | 2019-10-18 16:30 | SARD | COAC | Look Up | 45 | Valid on Working days from 07:30 till 16:30 | Working days |  |  | 07:30 - 16:30 | Planned | v.1 - 30/05/2019 18:00
CA-201801335 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Upgrading | 2019-09-08 08:00 | 2019-09-08 12:00 | SARD | COAC | Look Up | 0 | Valid on Working days from 08:00 till 12:00 | Working days |  |  | 08:00 - 12:00 | Planned | v.1 - 30/05/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801338 | --- | AC Link | IntraZonal | Upgrading | 2019-10-21 07:30 | 2019-10-26 16:30 | SARD | COAC | Look Up | 90 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 70 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801351 | --- | AC Link | IntraZonal | Upgrading | 2019-11-18 07:30 | 2019-11-20 16:30 | SARD | COAC | Look Up | 85 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 65 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801355 | --- | AC Link | IntraZonal | Upgrading | 2019-11-25 07:30 | 2019-11-29 16:30 | SARD | COAC | Look Up | 80 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CA-201801360 | --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link Substation AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | CSUD | SARD | Look Up | 270 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/06/2019 18:00
CA-201801360 | --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link Substation AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | CSUD | SARD | Look Up | 270 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/06/2019 18:00
CA-201801360 | --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link Substation AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | SARD | CSUD | Look Up | 300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 25/06/2019 18:00
CA-201801360 | --- --- --- --- --- --- --- | AC Link AC Link AC Link AC Link AC Link Substation AC Link | IntraZonal IntraZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-07-05 16:00 | 2019-07-19 16:00 | SARD | CSUD | Look Up | 300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 25/06/2019 18:00
CA-201801365 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801365 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801365 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801365 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-09 08:00 | 2019-09-16 08:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CNOR | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CNOR | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | CNOR | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | CNOR | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | CORS | SARD | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801366 | --- --- --- --- --- --- | DC Link AC Link AC Link DC Link DC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-10-04 16:00 | SARD | CORS | Look Up | 0 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CA-201801373 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-11-21 08:00 | 2019-11-21 17:00 | SARD | COAC | Look Up | 35 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 30/05/2019 18:00
CA-201801374 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-11-22 08:00 | 2019-11-22 17:00 | SARD | COAC | Look Up | 40 | Valid on Working days from 08:00 till 17:00 | Working days |  |  | 08:00 - 17:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801949 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801949 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801949 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801949 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801950 | --- --- --- --- --- --- | AC Link AC Link Substation Substation AC Link Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-12 08:00 | 2019-10-16 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 100 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 00:00 till 06:59 | Holidays |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 100 | Valid on Holidays from 07:00 till 22:59 | Holidays |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801951 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | ROSN | SICI | Look Up | 300 | Valid on Holidays from 23:00 till 23:59 | Holidays |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 00:00 till 06:59 | Working days |  |  | 00:00 - 06:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 250 | Valid on Working days from 07:00 till 22:59 | Working days |  |  | 07:00 - 22:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Working days from 23:00 till 23:59 | Working days |  |  | 23:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801952 | --- --- --- --- --- | AC Link AC Link AC Link Substation Substation | CrossZonal CrossZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-10-16 16:00 | 2019-10-20 16:00 | SICI | ROSN | Look Up | 100 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801958 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-07-27 08:00 | 2019-07-28 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Updated | v.2 - 06/06/2019 17:00 v.1 - 30/05/2019 18:00
CC-201801958 | --- --- | AC Link AC Link | IntraZonal IntraZonal | Maintenance | 2019-07-27 08:00 | 2019-07-28 16:00 | SUD | CSUD | Look Up | 3400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Updated | v.2 - 06/06/2019 17:00 v.1 - 30/05/2019 18:00
CC-201801959 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-03 07:00 | 2019-08-13 17:00 | SUD | CSUD | Look Up | 4000 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801959 | --- --- --- --- --- | Substation AC Link Substation AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-03 07:00 | 2019-08-13 17:00 | SUD | CSUD | Look Up | 4000 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801960 | --- --- --- --- | AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-08-19 08:00 | 2019-09-06 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801960 | --- --- --- --- | AC Link AC Link AC Link AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-08-19 08:00 | 2019-09-06 16:00 | SUD | CSUD | Look Up | 3600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801961 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-27 08:00 | 2019-09-15 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801961 | --- --- --- | AC Link AC Link Substation | IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-27 08:00 | 2019-09-15 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801962 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801962 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801962 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801962 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-11-25 10:00 | 2019-12-06 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801964 | --- --- --- --- | Substation Substation Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Maintenance | 2019-10-12 08:00 | 2019-10-13 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201801965 | --- --- --- --- | AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 08:00 | 2019-10-13 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201801965 | --- --- --- --- | AC Link AC Link Substation AC Link | IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-09-30 08:00 | 2019-10-13 16:00 | SUD | CSUD | Look Up | 3900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201802048 | --- | Substation | IntraZonal | Maintenance | 2019-11-07 09:00 | 2019-11-07 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Updated | v.2 - 11/06/2019 18:00 v.1 - 30/05/2019 18:00
CC-201802048 | --- | Substation | IntraZonal | Maintenance | 2019-11-07 09:00 | 2019-11-07 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Working days from 09:00 till 16:00 | Working days |  |  | 09:00 - 16:00 | Updated | v.2 - 11/06/2019 18:00 v.1 - 30/05/2019 18:00
CC-201900382 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900382 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900382 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900382 | --- --- --- | AC Link AC Link Substation | IntraZonal CrossZonal IntraZonal | Maintenance | 2019-10-25 08:00 | 2019-10-31 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900777 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-09-20 16:00 | ROSN | SICI | Look Up | 750 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900777 | --- --- | Substation Substation | IntraZonal IntraZonal | Maintenance | 2019-09-16 08:00 | 2019-09-20 16:00 | SICI | ROSN | Look Up | 750 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 30/05/2019 18:00
CC-201900860 | --- | AC Link | CrossZonal | Maintenance | 2019-07-14 08:00 | 2019-07-14 16:00 | ROSN | SUD | Look Up | 900 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201900860 | --- | AC Link | CrossZonal | Maintenance | 2019-07-14 08:00 | 2019-07-14 16:00 | SUD | CSUD | Look Up | 3300 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Planned | v.1 - 30/05/2019 18:00
CC-201900901 | --- | Substation | IntraZonal | Maintenance | 2019-10-11 08:00 | 2019-10-11 16:00 | CNOR | CSUD | Look Up | 800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 31/05/2019 17:00
CC-201900901 | --- | Substation | IntraZonal | Maintenance | 2019-10-11 08:00 | 2019-10-11 16:00 | CNOR | NORD | Look Up | 1200 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 31/05/2019 17:00
CC-201900901 | --- | Substation | IntraZonal | Maintenance | 2019-10-11 08:00 | 2019-10-11 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 31/05/2019 17:00
CC-201900901 | --- | Substation | IntraZonal | Maintenance | 2019-10-11 08:00 | 2019-10-11 16:00 | NORD | CNOR | Look Up | 2400 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 31/05/2019 17:00
CC-201900903 | --- | Substation | IntraZonal | Maintenance | 2019-07-14 08:00 | 2019-07-14 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Cancelled | v.2 - 05/07/2019 17:00 v.1 - 31/05/2019 17:00
CC-201900903 | --- | Substation | IntraZonal | Maintenance | 2019-07-14 08:00 | 2019-07-14 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Holidays from 08:00 till 16:00 | Holidays |  |  | 08:00 - 16:00 | Cancelled | v.2 - 05/07/2019 17:00 v.1 - 31/05/2019 17:00
CC-201900929 | --- | AC Link | CrossZonal | Upgrading | 2019-10-01 08:00 | 2019-10-10 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 07/06/2019 17:00
CC-201900929 | --- | AC Link | CrossZonal | Upgrading | 2019-10-01 08:00 | 2019-10-10 16:00 | CSUD | CNOR | Look Up | 1600 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 07/06/2019 17:00
CC-201900977 | --- | Substation | IntraZonal | Maintenance | 2019-11-04 08:00 | 2019-11-06 16:00 | SUD | CSUD | Look Up | 2300 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 11/06/2019 18:00
CC-201901011 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-09-09 08:00 | 2019-09-23 16:00 | ROSN | SUD | Look Up | 900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/06/2019 17:00
CC-201901011 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-09-09 08:00 | 2019-09-23 16:00 | ROSN | SUD | Look Up | 900 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 18/06/2019 17:00
CC-201901011 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-09-09 08:00 | 2019-09-23 16:00 | SUD | CSUD | Look Up | 3300 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 18/06/2019 17:00
CC-201901011 | --- --- | AC Link AC Link | CrossZonal CrossZonal | Upgrading | 2019-09-09 08:00 | 2019-09-23 16:00 | SUD | CSUD | Look Up | 3300 | Valid on Holidays from 00:00 till 23:59 | Holidays |  |  | 00:00 - 23:59 | Planned | v.1 - 18/06/2019 17:00
CC-201901109 | --- | Substation | IntraZonal | Maintenance | 2019-11-11 08:00 | 2019-11-15 17:00 | CNOR | NORD | Look Up | 1900 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CC-201901109 | --- | Substation | IntraZonal | Maintenance | 2019-11-11 08:00 | 2019-11-15 17:00 | NORD | CNOR | Look Up | 2800 | Valid on Working days from 00:00 till 23:59 | Working days |  |  | 00:00 - 23:59 | Planned | v.1 - 05/07/2019 17:00
CC-201901121 | --- --- --- --- --- | AC Link Substation Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-19 08:00 | 2019-08-19 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/07/2019 17:00
CC-201901121 | --- --- --- --- --- | AC Link Substation Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-19 08:00 | 2019-08-19 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/07/2019 17:00
CC-201901122 | --- --- --- --- --- | AC Link Substation Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-24 08:00 | 2019-08-24 16:00 | CNOR | NORD | Look Up | 1800 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/07/2019 17:00
CC-201901122 | --- --- --- --- --- | AC Link Substation Substation AC Link Substation | IntraZonal IntraZonal IntraZonal IntraZonal IntraZonal | Upgrading | 2019-08-24 08:00 | 2019-08-24 16:00 | NORD | CNOR | Look Up | 2600 | Valid on Working days from 08:00 till 16:00 | Working days |  |  | 08:00 - 16:00 | Planned | v.1 - 09/07/2019 17:00
CC-201901124 | --- | AC Link | IntraZonal | Maintenance | 2019-10-05 08:00 | 2019-10-05 15:00 | SUD | CSUD | Look Up | 3600 | Valid on Working days from 08:00 till 15:00 | Working days |  |  | 08:00 - 15:00 | Planned | v.1 - 09/07/2019 17:00